## Summary
PROJECT CONSTRUCTION SCHEDULE — SUMMARY
Project ID: 6a4613ac628b203b4b578111 ¦ Start: 02 Jul 2026 ¦ End: 10 Sep 2026 ¦ Duration: 71 days
Stage | Phase | Start | Finish | Duration | Float | Critical | Predecessors | Remarks
Foundation | Substructure | 2026-07-02 | 2026-07-29 | 28 | 0 | CRITICAL | —
Plinth Beam | Substructure | 2026-07-30 | 2026-08-01 | 3 | 0 | CRITICAL | Foundation
GF Columns | Superstructure | 2026-08-02 | 2026-08-04 | 3 | 0 | CRITICAL | Plinth Beam
GF Beams & Slab | Superstructure | 2026-08-05 | 2026-08-07 | 3 | 0 | CRITICAL | GF Columns | Monolithic cast with slab
Staircase | Superstructure | 2026-08-05 | 2026-08-07 | 3 | 34 | Normal | GF Columns | Can start 34d later
Lintel Beams | Superstructure | 2026-08-08 | 2026-08-10 | 3 | 0 | CRITICAL | GF Beams & Slab
Walls | Masonry | 2026-08-11 | 2026-08-11 | 1 | 0 | CRITICAL | Lintel Beams
Subfloor | Masonry | 2026-08-12 | 2026-08-14 | 3 | 8 | Normal | Walls | Can start 8d later
Plumbing | Services | 2026-08-12 | 2026-08-21 | 10 | 0 | CRITICAL | Walls | Assumed — subcontractor
Wiring | Services | 2026-08-12 | 2026-08-21 | 10 | 0 | CRITICAL | Walls | Assumed — subcontractor
External Plaster | Finishes | 2026-08-12 | 2026-08-12 | 1 | 0 | CRITICAL | Walls
Internal Plaster | Finishes | 2026-08-22 | 2026-08-22 | 1 | 0 | CRITICAL | Plumbing, Wiring
Floor Tiles | Finishes | 2026-08-23 | 2026-08-23 | 1 | 0 | CRITICAL | Internal Plaster, Subfloor
External Painting | Finishes | 2026-08-13 | 2026-08-13 | 1 | 28 | Normal | External Plaster | Can start 28d later
Wall Tiles | Finishes | 2026-08-24 | 2026-09-02 | 10 | 0 | CRITICAL | Floor Tiles
Internal Painting | Finishes | 2026-08-24 | 2026-08-24 | 1 | 0 | CRITICAL | Floor Tiles
Sanitary Fittings | Fittings | 2026-09-03 | 2026-09-07 | 5 | 0 | CRITICAL | Wall Tiles
Light Fittings | Fittings | 2026-08-25 | 2026-08-29 | 5 | 9 | Normal | Internal Painting | Can start 9d later
Cleaning | Handover | 2026-09-08 | 2026-09-10 | 3 | 0 | CRITICAL | Sanitary Fittings, Light Fittings

## Gantt Chart
BAR CHART PROGRAMME
Stage | Phase | Dur | Start | Finish | Bar (weeks →)
[6 empty] | W1 02 Jul | W2 09 Jul | W3 16 Jul | W4 23 Jul | W5 30 Jul | W6 06 Aug | W7 13 Aug | W8 20 Aug | W9 27 Aug | W10 03 Sep | W11 10 Sep | W12 17 Sep
— SUBSTRUCTURE —
Foundation | Substructure | 28 | 2026-07-02 | 2026-07-29 |  | █ | █ | █ | █
Plinth Beam | Substructure | 3 | 2026-07-30 | 2026-08-01 | [5 empty] | █
— SUPERSTRUCTURE —
GF Columns | Superstructure | 3 | 2026-08-02 | 2026-08-04
GF Beams & Slab | Superstructure | 3 | 2026-08-05 | 2026-08-07 | [6 empty] | █
Staircase | Superstructure | 3 | 2026-08-05 | 2026-08-07 | [6 empty] | █ | ░ | ░ | ░ | ░ | ░
Lintel Beams | Superstructure | 3 | 2026-08-08 | 2026-08-10
— MASONRY —
Walls | Masonry | 1 | 2026-08-11 | 2026-08-11
Subfloor | Masonry | 3 | 2026-08-12 | 2026-08-14 | [7 empty] | █ | ░
— SERVICES —
Plumbing | Services | 10 | 2026-08-12 | 2026-08-21 | [7 empty] | █ | █
Wiring | Services | 10 | 2026-08-12 | 2026-08-21 | [7 empty] | █ | █
— FINISHES —
External Plaster | Finishes | 1 | 2026-08-12 | 2026-08-12
Internal Plaster | Finishes | 1 | 2026-08-22 | 2026-08-22
Floor Tiles | Finishes | 1 | 2026-08-23 | 2026-08-23
External Painting | Finishes | 1 | 2026-08-13 | 2026-08-13 | [7 empty] | █ | ░ | ░ | ░ | ░
Wall Tiles | Finishes | 10 | 2026-08-24 | 2026-09-02 | [9 empty] | █
Internal Painting | Finishes | 1 | 2026-08-24 | 2026-08-24
— FITTINGS —
Sanitary Fittings | Fittings | 5 | 2026-09-03 | 2026-09-07 | [10 empty] | █
Light Fittings | Fittings | 5 | 2026-08-25 | 2026-08-29 | [9 empty] | █ | ░
— HANDOVER —
Cleaning | Handover | 3 | 2026-09-08 | 2026-09-10 | [11 empty] | █
Legend: █ = Activity duration ░ = Total float Red = Critical Phase colours as shown above

## Critical Path
CRITICAL PATH ACTIVITIES (Total Float = 0)
Stage | Phase | Activity | Qty | Unit | Duration | Early Start | Early Finish | Late Start | Late Finish | Gang
Foundation | Substructure | Excavation | 52.42 | cum | 12 | 2026-07-02 | 2026-07-13 | 2026-07-02 | 2026-07-13 | 4 helpers
Foundation | Substructure | PCC(1:4:8) | 5.23 | cum | 2 | 2026-07-14 | 2026-07-15 | 2026-07-14 | 2026-07-15 | 1 mason + 4 helpers
Foundation | Substructure | Footing main bars | 180.95 | kg | 1 | 2026-07-16 | 2026-07-16 | 2026-07-16 | 2026-07-16 | 2 bar benders
Foundation | Substructure | Footing Cross Reinforcement | 180.95 | kg | 1 | 2026-07-16 | 2026-07-16 | 2026-07-16 | 2026-07-16 | 2 bar benders
Foundation | Substructure | Pedestal Reinforcement | 146.67 | kg | 1 | 2026-07-16 | 2026-07-16 | 2026-07-16 | 2026-07-16 | 2 bar benders
Foundation | Substructure | Pedestal Stirrups | 69.16 | kg | 1 | 2026-07-16 | 2026-07-16 | 2026-07-16 | 2026-07-16 | 2 bar benders
Foundation | Substructure | FDNColumn Main Bars | 183.1 | kg | 1 | 2026-07-16 | 2026-07-16 | 2026-07-16 | 2026-07-16 | 2 bar benders
Foundation | Substructure | FDNColumn Stirrups | 31.91 | kg | 1 | 2026-07-16 | 2026-07-16 | 2026-07-16 | 2026-07-16 | 2 bar benders
Foundation | Substructure | Footing Formwork | 18.1 | m² | 1 | 2026-07-17 | 2026-07-17 | 2026-07-17 | 2026-07-17 | 2 carpenters
Foundation | Substructure | Pedestal Formwork | 9.09 | m² | 1 | 2026-07-17 | 2026-07-17 | 2026-07-17 | 2026-07-17 | 2 carpenters
Foundation | Substructure | FDNColumn Formwork | 17.09 | m² | 1 | 2026-07-17 | 2026-07-17 | 2026-07-17 | 2026-07-17 | 2 carpenters
Foundation | Substructure | FDN RCC(M25) | 10.47 | cum | 7 | 2026-07-18 | 2026-07-24 | 2026-07-18 | 2026-07-24 | 2 masons + 6 helpers
Foundation | Substructure | Pedestal RCC(M25) | 0.903 | cum | 3 | 2026-07-18 | 2026-07-20 | 2026-07-18 | 2026-07-20 | 1 mason + 4 helpers
Foundation | Substructure | FDNColumn RCC(M25) | 0.682 | cum | 3 | 2026-07-18 | 2026-07-20 | 2026-07-18 | 2026-07-20 | 1 mason + 4 helpers
Foundation | Substructure | RFR (Returning and Filling) | 38.65 | m³ | 5 | 2026-07-25 | 2026-07-29 | 2026-07-25 | 2026-07-29 | 4 helpers
Foundation | Substructure | Removal | 17.28 | m³ | 2 | 2026-07-25 | 2026-07-26 | 2026-07-25 | 2026-07-26 | 4 helpers
Plinth Beam | Substructure | Beam Main Bars | — |  | 1 | 2026-07-30 | 2026-07-30 | 2026-07-30 | 2026-07-30 | 2 bar benders
Plinth Beam | Substructure | Beam Extra Bars | — |  | 1 | 2026-07-30 | 2026-07-30 | 2026-07-30 | 2026-07-30 | 2 bar benders
Plinth Beam | Substructure | Beam Stirrups | — |  | 1 | 2026-07-30 | 2026-07-30 | 2026-07-30 | 2026-07-30 | 2 bar benders
Plinth Beam | Substructure | Beam Formwork | — |  | 1 | 2026-07-31 | 2026-07-31 | 2026-07-31 | 2026-07-31 | 3 carpenters
Plinth Beam | Substructure | Beam RCC(M25) | — |  | 1 | 2026-08-01 | 2026-08-01 | 2026-08-01 | 2026-08-01 | 2 masons + 6 helpers
GF Columns | Superstructure | Column Main Bars | — |  | 1 | 2026-08-02 | 2026-08-02 | 2026-08-02 | 2026-08-02 | 2 bar benders
GF Columns | Superstructure | Column Stirrups | — |  | 1 | 2026-08-02 | 2026-08-02 | 2026-08-02 | 2026-08-02 | 2 bar benders
GF Columns | Superstructure | Column Formwork | — |  | 1 | 2026-08-03 | 2026-08-03 | 2026-08-03 | 2026-08-03 | 2 carpenters
GF Columns | Superstructure | Column RCC(M25) | — |  | 1 | 2026-08-04 | 2026-08-04 | 2026-08-04 | 2026-08-04 | 2 masons + 4 helpers
GF Beams & Slab | Superstructure | Beam Main Bars | — |  | 1 | 2026-08-05 | 2026-08-05 | 2026-08-05 | 2026-08-05 | 2 bar benders
GF Beams & Slab | Superstructure | Beam Extra Bars | — |  | 1 | 2026-08-05 | 2026-08-05 | 2026-08-05 | 2026-08-05 | 2 bar benders
GF Beams & Slab | Superstructure | Beam Stirrups | — |  | 1 | 2026-08-05 | 2026-08-05 | 2026-08-05 | 2026-08-05 | 2 bar benders
GF Beams & Slab | Superstructure | Slab Main Bars | — |  | 1 | 2026-08-05 | 2026-08-05 | 2026-08-05 | 2026-08-05 | 3 bar benders
GF Beams & Slab | Superstructure | Slab Cross Bars | — |  | 1 | 2026-08-05 | 2026-08-05 | 2026-08-05 | 2026-08-05 | 3 bar benders
GF Beams & Slab | Superstructure | Beam Formwork | — |  | 1 | 2026-08-06 | 2026-08-06 | 2026-08-06 | 2026-08-06 | 3 carpenters
GF Beams & Slab | Superstructure | Slab Formwork | — |  | 1 | 2026-08-06 | 2026-08-06 | 2026-08-06 | 2026-08-06 | 3 carpenters
GF Beams & Slab | Superstructure | Beam RCC(M25) | — |  | 1 | 2026-08-07 | 2026-08-07 | 2026-08-07 | 2026-08-07 | 2 masons + 6 helpers
GF Beams & Slab | Superstructure | Slab RCC(M25) | — |  | 1 | 2026-08-07 | 2026-08-07 | 2026-08-07 | 2026-08-07 | 3 masons + 8 helpers
Lintel Beams | Superstructure | Beam Main Bars | — |  | 1 | 2026-08-08 | 2026-08-08 | 2026-08-08 | 2026-08-08 | 2 bar benders
Lintel Beams | Superstructure | Beam Stirrups | — |  | 1 | 2026-08-08 | 2026-08-08 | 2026-08-08 | 2026-08-08 | 2 bar benders
Lintel Beams | Superstructure | Beam Formwork | — |  | 1 | 2026-08-09 | 2026-08-09 | 2026-08-09 | 2026-08-09 | 3 carpenters
Lintel Beams | Superstructure | Beam RCC(M25) | — |  | 1 | 2026-08-10 | 2026-08-10 | 2026-08-10 | 2026-08-10 | 2 masons + 6 helpers
Walls | Masonry | Full Brick Wall | — |  | 1 | 2026-08-11 | 2026-08-11 | 2026-08-11 | 2026-08-11 | 2 masons + 4 helpers
Walls | Masonry | Half Brick Wall | — |  | 1 | 2026-08-11 | 2026-08-11 | 2026-08-11 | 2026-08-11 | 2 masons + 3 helpers
Plumbing | Services | Plumbing Rough-in | — |  | 7 | 2026-08-12 | 2026-08-18 | 2026-08-12 | 2026-08-18 | Subcontractor
Plumbing | Services | Plumbing Testing | — |  | 3 | 2026-08-19 | 2026-08-21 | 2026-08-19 | 2026-08-21 | Subcontractor
Wiring | Services | Wiring Rough-in | — |  | 7 | 2026-08-12 | 2026-08-18 | 2026-08-12 | 2026-08-18 | Subcontractor
Wiring | Services | Wiring Testing | — |  | 3 | 2026-08-19 | 2026-08-21 | 2026-08-19 | 2026-08-21 | Subcontractor
External Plaster | Finishes | External Plaster | — |  | 1 | 2026-08-12 | 2026-08-12 | 2026-08-12 | 2026-08-12 | 2 masons + 2 helpers
Internal Plaster | Finishes | Internal Plaster | — |  | 1 | 2026-08-22 | 2026-08-22 | 2026-08-22 | 2026-08-22 | 2 masons + 2 helpers
Floor Tiles | Finishes | Floor Area | — |  | 1 | 2026-08-23 | 2026-08-23 | 2026-08-23 | 2026-08-23 | 2 masons + 2 helpers
Wall Tiles | Finishes | Wall Tiles | — |  | 10 | 2026-08-24 | 2026-09-02 | 2026-08-24 | 2026-09-02 | Subcontractor
Internal Painting | Finishes | Internal Painting | — |  | 1 | 2026-08-24 | 2026-08-24 | 2026-08-24 | 2026-08-24 | 2 painters
Internal Painting | Finishes | Wooden Door Painting | — |  | 1 | 2026-08-24 | 2026-08-24 | 2026-08-24 | 2026-08-24 | 2 painters
Sanitary Fittings | Fittings | Sanitary Fittings | — |  | 5 | 2026-09-03 | 2026-09-07 | 2026-09-03 | 2026-09-07 | Subcontractor
Cleaning | Handover | Cleaning & Handover | — |  | 3 | 2026-09-08 | 2026-09-10 | 2026-09-08 | 2026-09-10 | Subcontractor

## Foundation
FOUNDATION — ACTIVITY SCHEDULE
Activity | Qty | Unit | Duration | Early Start | Early Finish | Late Start | Late Finish | Total Float | Critical | Gang
Excavation | 52.42 | cum | 12 | 2026-07-02 | 2026-07-13 | 2026-07-02 | 2026-07-13 | 0 | CRITICAL | 4 helpers
PCC(1:4:8) | 5.23 | cum | 2 | 2026-07-14 | 2026-07-15 | 2026-07-14 | 2026-07-15 | 0 | CRITICAL | 1 mason + 4 helpers
Footing main bars | 180.95 | kg | 1 | 2026-07-16 | 2026-07-16 | 2026-07-16 | 2026-07-16 | 0 | CRITICAL | 2 bar benders
Footing Cross Reinforcement | 180.95 | kg | 1 | 2026-07-16 | 2026-07-16 | 2026-07-16 | 2026-07-16 | 0 | CRITICAL | 2 bar benders
Pedestal Reinforcement | 146.67 | kg | 1 | 2026-07-16 | 2026-07-16 | 2026-07-16 | 2026-07-16 | 0 | CRITICAL | 2 bar benders
Pedestal Stirrups | 69.16 | kg | 1 | 2026-07-16 | 2026-07-16 | 2026-07-16 | 2026-07-16 | 0 | CRITICAL | 2 bar benders
FDNColumn Main Bars | 183.1 | kg | 1 | 2026-07-16 | 2026-07-16 | 2026-07-16 | 2026-07-16 | 0 | CRITICAL | 2 bar benders
FDNColumn Stirrups | 31.91 | kg | 1 | 2026-07-16 | 2026-07-16 | 2026-07-16 | 2026-07-16 | 0 | CRITICAL | 2 bar benders
Footing Formwork | 18.1 | m² | 1 | 2026-07-17 | 2026-07-17 | 2026-07-17 | 2026-07-17 | 0 | CRITICAL | 2 carpenters
Pedestal Formwork | 9.09 | m² | 1 | 2026-07-17 | 2026-07-17 | 2026-07-17 | 2026-07-17 | 0 | CRITICAL | 2 carpenters
FDNColumn Formwork | 17.09 | m² | 1 | 2026-07-17 | 2026-07-17 | 2026-07-17 | 2026-07-17 | 0 | CRITICAL | 2 carpenters
FDN RCC(M25) | 10.47 | cum | 7 | 2026-07-18 | 2026-07-24 | 2026-07-18 | 2026-07-24 | 0 | CRITICAL | 2 masons + 6 helpers
Pedestal RCC(M25) | 0.903 | cum | 3 | 2026-07-18 | 2026-07-20 | 2026-07-18 | 2026-07-20 | 0 | CRITICAL | 1 mason + 4 helpers
FDNColumn RCC(M25) | 0.682 | cum | 3 | 2026-07-18 | 2026-07-20 | 2026-07-18 | 2026-07-20 | 0 | CRITICAL | 1 mason + 4 helpers
RFR (Returning and Filling) | 38.65 | m³ | 5 | 2026-07-25 | 2026-07-29 | 2026-07-25 | 2026-07-29 | 0 | CRITICAL | 4 helpers
Removal | 17.28 | m³ | 2 | 2026-07-25 | 2026-07-26 | 2026-07-25 | 2026-07-26 | 0 | CRITICAL | 4 helpers

## Plinth Beam
PLINTH BEAM — ACTIVITY SCHEDULE
Activity | Qty | Unit | Duration | Early Start | Early Finish | Late Start | Late Finish | Total Float | Critical | Gang
Beam Main Bars | — |  | 1 | 2026-07-30 | 2026-07-30 | 2026-07-30 | 2026-07-30 | 0 | CRITICAL | 2 bar benders
Beam Extra Bars | — |  | 1 | 2026-07-30 | 2026-07-30 | 2026-07-30 | 2026-07-30 | 0 | CRITICAL | 2 bar benders
Beam Stirrups | — |  | 1 | 2026-07-30 | 2026-07-30 | 2026-07-30 | 2026-07-30 | 0 | CRITICAL | 2 bar benders
Beam Formwork | — |  | 1 | 2026-07-31 | 2026-07-31 | 2026-07-31 | 2026-07-31 | 0 | CRITICAL | 3 carpenters
Beam RCC(M25) | — |  | 1 | 2026-08-01 | 2026-08-01 | 2026-08-01 | 2026-08-01 | 0 | CRITICAL | 2 masons + 6 helpers

## GF Columns
GF COLUMNS — ACTIVITY SCHEDULE
Activity | Qty | Unit | Duration | Early Start | Early Finish | Late Start | Late Finish | Total Float | Critical | Gang
Column Main Bars | — |  | 1 | 2026-08-02 | 2026-08-02 | 2026-08-02 | 2026-08-02 | 0 | CRITICAL | 2 bar benders
Column Stirrups | — |  | 1 | 2026-08-02 | 2026-08-02 | 2026-08-02 | 2026-08-02 | 0 | CRITICAL | 2 bar benders
Column Formwork | — |  | 1 | 2026-08-03 | 2026-08-03 | 2026-08-03 | 2026-08-03 | 0 | CRITICAL | 2 carpenters
Column RCC(M25) | — |  | 1 | 2026-08-04 | 2026-08-04 | 2026-08-04 | 2026-08-04 | 0 | CRITICAL | 2 masons + 4 helpers

## GF Beams & Slab
GF BEAMS & SLAB — ACTIVITY SCHEDULE
Activity | Qty | Unit | Duration | Early Start | Early Finish | Late Start | Late Finish | Total Float | Critical | Gang
Beam Main Bars | — |  | 1 | 2026-08-05 | 2026-08-05 | 2026-08-05 | 2026-08-05 | 0 | CRITICAL | 2 bar benders
Beam Extra Bars | — |  | 1 | 2026-08-05 | 2026-08-05 | 2026-08-05 | 2026-08-05 | 0 | CRITICAL | 2 bar benders
Beam Stirrups | — |  | 1 | 2026-08-05 | 2026-08-05 | 2026-08-05 | 2026-08-05 | 0 | CRITICAL | 2 bar benders
Slab Main Bars | — |  | 1 | 2026-08-05 | 2026-08-05 | 2026-08-05 | 2026-08-05 | 0 | CRITICAL | 3 bar benders
Slab Cross Bars | — |  | 1 | 2026-08-05 | 2026-08-05 | 2026-08-05 | 2026-08-05 | 0 | CRITICAL | 3 bar benders
Beam Formwork | — |  | 1 | 2026-08-06 | 2026-08-06 | 2026-08-06 | 2026-08-06 | 0 | CRITICAL | 3 carpenters
Slab Formwork | — |  | 1 | 2026-08-06 | 2026-08-06 | 2026-08-06 | 2026-08-06 | 0 | CRITICAL | 3 carpenters
Beam RCC(M25) | — |  | 1 | 2026-08-07 | 2026-08-07 | 2026-08-07 | 2026-08-07 | 0 | CRITICAL | 2 masons + 6 helpers
Slab RCC(M25) | — |  | 1 | 2026-08-07 | 2026-08-07 | 2026-08-07 | 2026-08-07 | 0 | CRITICAL | 3 masons + 8 helpers

## Staircase
STAIRCASE — ACTIVITY SCHEDULE
Activity | Qty | Unit | Duration | Early Start | Early Finish | Late Start | Late Finish | Total Float | Critical | Gang
Beam Main Bars | — |  | 1 | 2026-08-05 | 2026-08-05 | 2026-09-08 | 2026-09-08 | 34 | +34d | 2 bar benders
Beam Formwork | — |  | 1 | 2026-08-06 | 2026-08-06 | 2026-09-09 | 2026-09-09 | 34 | +34d | 3 carpenters
Beam RCC(M25) | — |  | 1 | 2026-08-07 | 2026-08-07 | 2026-09-10 | 2026-09-10 | 34 | +34d | 2 masons + 6 helpers

## Lintel Beams
LINTEL BEAMS — ACTIVITY SCHEDULE
Activity | Qty | Unit | Duration | Early Start | Early Finish | Late Start | Late Finish | Total Float | Critical | Gang
Beam Main Bars | — |  | 1 | 2026-08-08 | 2026-08-08 | 2026-08-08 | 2026-08-08 | 0 | CRITICAL | 2 bar benders
Beam Stirrups | — |  | 1 | 2026-08-08 | 2026-08-08 | 2026-08-08 | 2026-08-08 | 0 | CRITICAL | 2 bar benders
Beam Formwork | — |  | 1 | 2026-08-09 | 2026-08-09 | 2026-08-09 | 2026-08-09 | 0 | CRITICAL | 3 carpenters
Beam RCC(M25) | — |  | 1 | 2026-08-10 | 2026-08-10 | 2026-08-10 | 2026-08-10 | 0 | CRITICAL | 2 masons + 6 helpers

## Walls
WALLS — ACTIVITY SCHEDULE
Activity | Qty | Unit | Duration | Early Start | Early Finish | Late Start | Late Finish | Total Float | Critical | Gang
Full Brick Wall | — |  | 1 | 2026-08-11 | 2026-08-11 | 2026-08-11 | 2026-08-11 | 0 | CRITICAL | 2 masons + 4 helpers
Half Brick Wall | — |  | 1 | 2026-08-11 | 2026-08-11 | 2026-08-11 | 2026-08-11 | 0 | CRITICAL | 2 masons + 3 helpers

## Subfloor
SUBFLOOR — ACTIVITY SCHEDULE
Activity | Qty | Unit | Duration | Early Start | Early Finish | Late Start | Late Finish | Total Float | Critical | Gang
Subfloor Filling | — |  | 1 | 2026-08-12 | 2026-08-12 | 2026-08-20 | 2026-08-20 | 8 | +8d | 4 helpers
Subfloor PCC 1:3:6 | — |  | 1 | 2026-08-13 | 2026-08-13 | 2026-08-21 | 2026-08-21 | 8 | +8d | 1 mason + 4 helpers
Subfloor PCC 1:2:4 | — |  | 1 | 2026-08-13 | 2026-08-13 | 2026-08-21 | 2026-08-21 | 8 | +8d | 1 mason + 4 helpers
Cement Screed Bed | — |  | 1 | 2026-08-14 | 2026-08-14 | 2026-08-22 | 2026-08-22 | 8 | +8d | 2 masons

## Plumbing
PLUMBING — ACTIVITY SCHEDULE
Activity | Qty | Unit | Duration | Early Start | Early Finish | Late Start | Late Finish | Total Float | Critical | Gang
Plumbing Rough-in | — |  | 7 | 2026-08-12 | 2026-08-18 | 2026-08-12 | 2026-08-18 | 0 | CRITICAL | Subcontractor (assumed)
Plumbing Testing | — |  | 3 | 2026-08-19 | 2026-08-21 | 2026-08-19 | 2026-08-21 | 0 | CRITICAL | Subcontractor (assumed)

## Wiring
WIRING — ACTIVITY SCHEDULE
Activity | Qty | Unit | Duration | Early Start | Early Finish | Late Start | Late Finish | Total Float | Critical | Gang
Wiring Rough-in | — |  | 7 | 2026-08-12 | 2026-08-18 | 2026-08-12 | 2026-08-18 | 0 | CRITICAL | Subcontractor (assumed)
Wiring Testing | — |  | 3 | 2026-08-19 | 2026-08-21 | 2026-08-19 | 2026-08-21 | 0 | CRITICAL | Subcontractor (assumed)

## External Plaster
EXTERNAL PLASTER — ACTIVITY SCHEDULE
Activity | Qty | Unit | Duration | Early Start | Early Finish | Late Start | Late Finish | Total Float | Critical | Gang
External Plaster | — |  | 1 | 2026-08-12 | 2026-08-12 | 2026-08-12 | 2026-08-12 | 0 | CRITICAL | 2 masons + 2 helpers

## Internal Plaster
INTERNAL PLASTER — ACTIVITY SCHEDULE
Activity | Qty | Unit | Duration | Early Start | Early Finish | Late Start | Late Finish | Total Float | Critical | Gang
Internal Plaster | — |  | 1 | 2026-08-22 | 2026-08-22 | 2026-08-22 | 2026-08-22 | 0 | CRITICAL | 2 masons + 2 helpers

## Floor Tiles
FLOOR TILES — ACTIVITY SCHEDULE
Activity | Qty | Unit | Duration | Early Start | Early Finish | Late Start | Late Finish | Total Float | Critical | Gang
Floor Area | — |  | 1 | 2026-08-23 | 2026-08-23 | 2026-08-23 | 2026-08-23 | 0 | CRITICAL | 2 masons + 2 helpers

## External Painting
EXTERNAL PAINTING — ACTIVITY SCHEDULE
Activity | Qty | Unit | Duration | Early Start | Early Finish | Late Start | Late Finish | Total Float | Critical | Gang
External Painting | — |  | 1 | 2026-08-13 | 2026-08-13 | 2026-09-10 | 2026-09-10 | 28 | +28d | 2 painters

## Wall Tiles
WALL TILES — ACTIVITY SCHEDULE
Activity | Qty | Unit | Duration | Early Start | Early Finish | Late Start | Late Finish | Total Float | Critical | Gang
Wall Tiles | — |  | 10 | 2026-08-24 | 2026-09-02 | 2026-08-24 | 2026-09-02 | 0 | CRITICAL | Subcontractor (assumed)

## Internal Painting
INTERNAL PAINTING — ACTIVITY SCHEDULE
Activity | Qty | Unit | Duration | Early Start | Early Finish | Late Start | Late Finish | Total Float | Critical | Gang
Internal Painting | — |  | 1 | 2026-08-24 | 2026-08-24 | 2026-08-24 | 2026-08-24 | 0 | CRITICAL | 2 painters
Wooden Door Painting | — |  | 1 | 2026-08-24 | 2026-08-24 | 2026-08-24 | 2026-08-24 | 0 | CRITICAL | 2 painters

## Sanitary Fittings
SANITARY FITTINGS — ACTIVITY SCHEDULE
Activity | Qty | Unit | Duration | Early Start | Early Finish | Late Start | Late Finish | Total Float | Critical | Gang
Sanitary Fittings | — |  | 5 | 2026-09-03 | 2026-09-07 | 2026-09-03 | 2026-09-07 | 0 | CRITICAL | Subcontractor (assumed)

## Light Fittings
LIGHT FITTINGS — ACTIVITY SCHEDULE
Activity | Qty | Unit | Duration | Early Start | Early Finish | Late Start | Late Finish | Total Float | Critical | Gang
Light Fittings | — |  | 5 | 2026-08-25 | 2026-08-29 | 2026-09-03 | 2026-09-07 | 9 | +9d | Subcontractor (assumed)

## Cleaning
CLEANING — ACTIVITY SCHEDULE
Activity | Qty | Unit | Duration | Early Start | Early Finish | Late Start | Late Finish | Total Float | Critical | Gang
Cleaning & Handover | — |  | 3 | 2026-09-08 | 2026-09-10 | 2026-09-08 | 2026-09-10 | 0 | CRITICAL | Subcontractor (assumed)

## Productivity Used
PRODUCTIVITY CONSTANTS (NBC/IS Standards)
Activity | Rate | Unit | Min Days (NBC) | Gang
Excavation | 4.5 | cum | 1 | 4 helpers
PCC(1:4:8) | 3 | cum | 1 | 1 mason + 4 helpers
FDN RCC(M25) | 2.5 | cum | 7 | 2 masons + 6 helpers
Pedestal RCC(M25) | 2 | cum | 3 | 1 mason + 4 helpers
FDNColumn RCC(M25) | 2 | cum | 3 | 1 mason + 4 helpers
Footing main bars | 200 | kg | 1 | 2 bar benders
Footing Cross Reinforcement | 200 | kg | 1 | 2 bar benders
Pedestal Reinforcement | 200 | kg | 1 | 2 bar benders
Pedestal Stirrups | 150 | kg | 1 | 2 bar benders
FDNColumn Main Bars | 200 | kg | 1 | 2 bar benders
FDNColumn Stirrups | 150 | kg | 1 | 2 bar benders
Footing Formwork | 25 | sqm | 1 | 2 carpenters
Pedestal Formwork | 20 | sqm | 1 | 2 carpenters
FDNColumn Formwork | 20 | sqm | 1 | 2 carpenters
RFR (Returning and Filling) | 8 | cum | 1 | 4 helpers
Removal | 10 | cum | 1 | 4 helpers
Beam RCC(M25) | 2 | cum | 7 | 2 masons + 6 helpers
Beam Formwork | 30 | sqm | 1 | 3 carpenters
Beam Main Bars | 220 | kg | 1 | 2 bar benders
Beam Extra Bars | 220 | kg | 1 | 2 bar benders
Beam Stirrups | 180 | kg | 1 | 2 bar benders
Beam Total Steel | 220 | kg | 1 | 2 bar benders
Slab RCC(M25) | 3.5 | cum | 14 | 3 masons + 8 helpers
Slab Main Bars | 250 | kg | 1 | 3 bar benders
Slab Cross Bars | 250 | kg | 1 | 3 bar benders
Slab Formwork | 40 | sqm | 1 | 3 carpenters
Slab Total Steel | 250 | kg | 1 | 3 bar benders
Column RCC(M25) | 1.5 | cum | 7 | 2 masons + 4 helpers
Column Main Bars | 200 | kg | 1 | 2 bar benders
Column Stirrups | 150 | kg | 1 | 2 bar benders
Column Formwork | 22 | sqm | 1 | 2 carpenters
Column Total Steel | 200 | kg | 1 | 2 bar benders
Full Brick Wall | 2.5 | cum | 3 | 2 masons + 4 helpers
Half Brick Wall | 3 | cum | 2 | 2 masons + 3 helpers
Subfloor Filling | 6 | cum | 1 | 4 helpers
Subfloor PCC 1:3:6 | 2.5 | cum | 1 | 1 mason + 4 helpers
Subfloor PCC 1:2:4 | 2 | cum | 1 | 1 mason + 4 helpers
Cement Screed Bed | 15 | sqm | 2 | 2 masons
Floor Area | 12 | sqm | 1 | 2 masons + 2 helpers
Wooden Door Shutter | 4 | sqm | 1 | 2 carpenters
Wooden Door Frame | 0.05 | cum | 1 | 2 carpenters
UPVC Toilet Door | 4 | sqm | 1 | 2 carpenters
UPVC Windows | 8 | sqm | 1 | 2 carpenters
UPVC Ventilators | 6 | sqm | 1 | 2 carpenters
External Plaster | 20 | sqm | 1 | 2 masons + 2 helpers
Internal Plaster | 18 | sqm | 1 | 2 masons + 2 helpers
External Painting | 40 | sqm | 1 | 2 painters
Internal Painting | 35 | sqm | 1 | 2 painters
Wooden Door Painting | 12 | sqm | 1 | 2 painters