## Summary
PROJECT CONSTRUCTION SCHEDULE — SUMMARY
Project ID: 6a604af51bbc14bb70784e7f ¦ Start: 23 Jul 2026 ¦ End: 11 Dec 2026 ¦ Duration: 142 days
Stage | Phase | Start | Finish | Duration | Float | Critical | Predecessors | Remarks
Foundation | Substructure | 2026-07-23 | 2026-08-19 | 28 | 0 | CRITICAL | —
Plinth Beam | Substructure | 2026-08-20 | 2026-09-05 | 17 | 0 | CRITICAL | Foundation
GF Columns | Superstructure | 2026-09-06 | 2026-09-16 | 11 | 0 | CRITICAL | Plinth Beam
GF Beams & Slab | Superstructure | 2026-09-17 | 2026-09-27 | 11 | 0 | CRITICAL | GF Columns | Monolithic cast with slab
Staircase | Superstructure | 2026-09-17 | 2026-09-19 | 3 | 83 | Normal | GF Columns | Can start 83d later
Lintel Beams | Superstructure | 2026-09-28 | 2026-09-30 | 3 | 0 | CRITICAL | GF Beams & Slab
Walls | Masonry | 2026-10-01 | 2026-10-17 | 17 | 0 | CRITICAL | Lintel Beams
Subfloor | Masonry | 2026-10-18 | 2026-10-30 | 13 | 12 | Normal | Walls | Can start 12d later
Plumbing | Services | 2026-10-18 | 2026-10-27 | 10 | 0 | CRITICAL | Walls | Assumed — subcontractor
Wiring | Services | 2026-10-18 | 2026-10-27 | 10 | 0 | CRITICAL | Walls | Assumed — subcontractor
External Plaster | Finishes | 2026-10-18 | 2026-10-24 | 7 | 0 | CRITICAL | Walls
Internal Plaster | Finishes | 2026-10-28 | 2026-11-11 | 15 | 0 | CRITICAL | Plumbing, Wiring
Floor Tiles | Finishes | 2026-11-12 | 2026-11-23 | 12 | 0 | CRITICAL | Internal Plaster, Subfloor
External Painting | Finishes | 2026-10-25 | 2026-10-28 | 4 | 44 | Normal | External Plaster | Can start 44d later
Wall Tiles | Finishes | 2026-11-24 | 2026-12-03 | 10 | 0 | CRITICAL | Floor Tiles
Internal Painting | Finishes | 2026-11-24 | 2026-12-01 | 8 | 0 | CRITICAL | Floor Tiles
Sanitary Fittings | Fittings | 2026-12-04 | 2026-12-08 | 5 | 0 | CRITICAL | Wall Tiles
Light Fittings | Fittings | 2026-12-02 | 2026-12-06 | 5 | 2 | Normal | Internal Painting | Can start 2d later
Cleaning | Handover | 2026-12-09 | 2026-12-11 | 3 | 0 | CRITICAL | Sanitary Fittings, Light Fittings

## Gantt Chart
BAR CHART PROGRAMME
Stage | Phase | Dur | Start | Finish | Bar (weeks →)
[6 empty] | W1 23 Jul | W2 30 Jul | W3 06 Aug | W4 13 Aug | W5 20 Aug | W6 27 Aug | W7 03 Sep | W8 10 Sep | W9 17 Sep | W10 24 Sep | W11 01 Oct | W12 08 Oct | W13 15 Oct | W14 22 Oct | W15 29 Oct | W16 05 Nov | W17 12 Nov | W18 19 Nov | W19 26 Nov | W20 03 Dec | W21 10 Dec | W22 17 Dec
— SUBSTRUCTURE —
Foundation | Substructure | 28 | 2026-07-23 | 2026-08-19 |  | █ | █ | █ | █
Plinth Beam | Substructure | 17 | 2026-08-20 | 2026-09-05 | [5 empty] | █ | █ | █
— SUPERSTRUCTURE —
GF Columns | Superstructure | 11 | 2026-09-06 | 2026-09-16 | [8 empty] | █
GF Beams & Slab | Superstructure | 11 | 2026-09-17 | 2026-09-27 | [9 empty] | █ | █
Staircase | Superstructure | 3 | 2026-09-17 | 2026-09-19 | [9 empty] | █ | ░ | ░ | ░ | ░ | ░ | ░ | ░ | ░ | ░ | ░ | ░ | ░
Lintel Beams | Superstructure | 3 | 2026-09-28 | 2026-09-30
— MASONRY —
Walls | Masonry | 17 | 2026-10-01 | 2026-10-17 | [11 empty] | █ | █ | █
Subfloor | Masonry | 13 | 2026-10-18 | 2026-10-30 | [14 empty] | █ | █ | ░
— SERVICES —
Plumbing | Services | 10 | 2026-10-18 | 2026-10-27 | [14 empty] | █
Wiring | Services | 10 | 2026-10-18 | 2026-10-27 | [14 empty] | █
— FINISHES —
External Plaster | Finishes | 7 | 2026-10-18 | 2026-10-24 | [14 empty] | █
Internal Plaster | Finishes | 15 | 2026-10-28 | 2026-11-11 | [15 empty] | █ | █
Floor Tiles | Finishes | 12 | 2026-11-12 | 2026-11-23 | [17 empty] | █ | █
External Painting | Finishes | 4 | 2026-10-25 | 2026-10-28 | [15 empty] | ░ | ░ | ░ | ░ | ░ | ░ | ░
Wall Tiles | Finishes | 10 | 2026-11-24 | 2026-12-03 | [19 empty] | █ | █
Internal Painting | Finishes | 8 | 2026-11-24 | 2026-12-01 | [19 empty] | █
— FITTINGS —
Sanitary Fittings | Fittings | 5 | 2026-12-04 | 2026-12-08
Light Fittings | Fittings | 5 | 2026-12-02 | 2026-12-06 | [20 empty] | █
— HANDOVER —
Cleaning | Handover | 3 | 2026-12-09 | 2026-12-11 | [21 empty] | █
Legend: █ = Activity duration ░ = Total float Red = Critical Phase colours as shown above

## Critical Path
CRITICAL PATH ACTIVITIES (Total Float = 0)
Stage | Phase | Activity | Qty | Unit | Duration | Early Start | Early Finish | Late Start | Late Finish | Gang
Foundation | Substructure | Excavation | 52.42 | cum | 12 | 2026-07-23 | 2026-08-03 | 2026-07-23 | 2026-08-03 | 4 helpers
Foundation | Substructure | PCC(1:4:8) | 5.23 | cum | 2 | 2026-08-04 | 2026-08-05 | 2026-08-04 | 2026-08-05 | 1 mason + 4 helpers
Foundation | Substructure | Footing main bars | 180.95 | kg | 1 | 2026-08-06 | 2026-08-06 | 2026-08-06 | 2026-08-06 | 2 bar benders
Foundation | Substructure | Footing Cross Reinforcement | 180.95 | kg | 1 | 2026-08-06 | 2026-08-06 | 2026-08-06 | 2026-08-06 | 2 bar benders
Foundation | Substructure | Pedestal Reinforcement | 134.45 | kg | 1 | 2026-08-06 | 2026-08-06 | 2026-08-06 | 2026-08-06 | 2 bar benders
Foundation | Substructure | Pedestal Stirrups | 64.69 | kg | 1 | 2026-08-06 | 2026-08-06 | 2026-08-06 | 2026-08-06 | 2 bar benders
Foundation | Substructure | FDNColumn Main Bars | 169.82 | kg | 1 | 2026-08-06 | 2026-08-06 | 2026-08-06 | 2026-08-06 | 2 bar benders
Foundation | Substructure | FDNColumn Stirrups | 30.32 | kg | 1 | 2026-08-06 | 2026-08-06 | 2026-08-06 | 2026-08-06 | 2 bar benders
Foundation | Substructure | Footing Formwork | 18.1 | m² | 1 | 2026-08-07 | 2026-08-07 | 2026-08-07 | 2026-08-07 | 2 carpenters
Foundation | Substructure | Pedestal Formwork | 8.49 | m² | 1 | 2026-08-07 | 2026-08-07 | 2026-08-07 | 2026-08-07 | 2 carpenters
Foundation | Substructure | FDNColumn Formwork | 16.21 | m² | 1 | 2026-08-07 | 2026-08-07 | 2026-08-07 | 2026-08-07 | 2 carpenters
Foundation | Substructure | FDN RCC(M25) | 10.47 | cum | 7 | 2026-08-08 | 2026-08-14 | 2026-08-08 | 2026-08-14 | 2 masons + 6 helpers
Foundation | Substructure | Pedestal RCC(M25) | 0.844 | cum | 3 | 2026-08-08 | 2026-08-10 | 2026-08-08 | 2026-08-10 | 1 mason + 4 helpers
Foundation | Substructure | FDNColumn RCC(M25) | 0.651 | cum | 3 | 2026-08-08 | 2026-08-10 | 2026-08-08 | 2026-08-10 | 1 mason + 4 helpers
Foundation | Substructure | RFR (Returning and Filling) | 38.75 | m³ | 5 | 2026-08-15 | 2026-08-19 | 2026-08-15 | 2026-08-19 | 4 helpers
Foundation | Substructure | Removal | 17.19 | m³ | 2 | 2026-08-15 | 2026-08-16 | 2026-08-15 | 2026-08-16 | 4 helpers
Plinth Beam | Substructure | Beam Main Bars | 991.32 | kg | 5 | 2026-08-20 | 2026-08-24 | 2026-08-20 | 2026-08-24 | 2 bar benders
Plinth Beam | Substructure | Beam Extra Bars | — | kg | 1 | 2026-08-20 | 2026-08-20 | 2026-08-20 | 2026-08-20 | 2 bar benders
Plinth Beam | Substructure | Beam Stirrups | 318.25 | kg | 2 | 2026-08-20 | 2026-08-21 | 2026-08-20 | 2026-08-21 | 2 bar benders
Plinth Beam | Substructure | Beam Formwork | 127.43 | m² | 5 | 2026-08-25 | 2026-08-29 | 2026-08-25 | 2026-08-29 | 3 carpenters
Plinth Beam | Substructure | Beam RCC(M25) | 11.4 | m³ | 7 | 2026-08-30 | 2026-09-05 | 2026-08-30 | 2026-09-05 | 2 masons + 6 helpers
GF Columns | Superstructure | Column Main Bars | 335.56 | kg | 2 | 2026-09-06 | 2026-09-07 | 2026-09-06 | 2026-09-07 | 2 bar benders
GF Columns | Superstructure | Column Stirrups | 94.54 | kg | 1 | 2026-09-06 | 2026-09-06 | 2026-09-06 | 2026-09-06 | 2 bar benders
GF Columns | Superstructure | Column Formwork | 31.17 | m² | 2 | 2026-09-08 | 2026-09-09 | 2026-09-08 | 2026-09-09 | 2 carpenters
GF Columns | Superstructure | Column RCC(M25) | 1.91 | m³ | 7 | 2026-09-10 | 2026-09-16 | 2026-09-10 | 2026-09-16 | 2 masons + 4 helpers
GF Beams & Slab | Superstructure | Beam Main Bars | 991.32 | kg | 2 | 2026-09-17 | 2026-09-18 | 2026-09-17 | 2026-09-18 | 2 bar benders
GF Beams & Slab | Superstructure | Beam Extra Bars | — | kg | 1 | 2026-09-17 | 2026-09-17 | 2026-09-17 | 2026-09-17 | 2 bar benders
GF Beams & Slab | Superstructure | Beam Stirrups | 318.25 | kg | 1 | 2026-09-17 | 2026-09-17 | 2026-09-17 | 2026-09-17 | 2 bar benders
GF Beams & Slab | Superstructure | Slab Main Bars | — |  | 1 | 2026-09-17 | 2026-09-17 | 2026-09-17 | 2026-09-17 | 3 bar benders
GF Beams & Slab | Superstructure | Slab Cross Bars | — |  | 1 | 2026-09-17 | 2026-09-17 | 2026-09-17 | 2026-09-17 | 3 bar benders
GF Beams & Slab | Superstructure | Beam Formwork | 127.43 | m² | 2 | 2026-09-19 | 2026-09-20 | 2026-09-19 | 2026-09-20 | 3 carpenters
GF Beams & Slab | Superstructure | Slab Formwork | 39.08 | m² | 1 | 2026-09-19 | 2026-09-19 | 2026-09-19 | 2026-09-19 | 3 carpenters
GF Beams & Slab | Superstructure | Beam RCC(M25) | 11.4 | m³ | 7 | 2026-09-21 | 2026-09-27 | 2026-09-21 | 2026-09-27 | 2 masons + 6 helpers
GF Beams & Slab | Superstructure | Slab RCC(M25) | — |  | 1 | 2026-09-21 | 2026-09-21 | 2026-09-21 | 2026-09-21 | 3 masons + 8 helpers
Lintel Beams | Superstructure | Beam Main Bars | — |  | 1 | 2026-09-28 | 2026-09-28 | 2026-09-28 | 2026-09-28 | 2 bar benders
Lintel Beams | Superstructure | Beam Stirrups | — |  | 1 | 2026-09-28 | 2026-09-28 | 2026-09-28 | 2026-09-28 | 2 bar benders
Lintel Beams | Superstructure | Beam Formwork | — |  | 1 | 2026-09-29 | 2026-09-29 | 2026-09-29 | 2026-09-29 | 3 carpenters
Lintel Beams | Superstructure | Beam RCC(M25) | — |  | 1 | 2026-09-30 | 2026-09-30 | 2026-09-30 | 2026-09-30 | 2 masons + 6 helpers
Walls | Masonry | Full Brick Wall | 41.919 | cum | 17 | 2026-10-01 | 2026-10-17 | 2026-10-01 | 2026-10-17 | 2 masons + 4 helpers
Walls | Masonry | Half Brick Wall | — | sqm | 1 | 2026-10-01 | 2026-10-01 | 2026-10-01 | 2026-10-01 | 2 masons + 3 helpers
Plumbing | Services | Plumbing Rough-in | — |  | 7 | 2026-10-18 | 2026-10-24 | 2026-10-18 | 2026-10-24 | Subcontractor
Plumbing | Services | Plumbing Testing | — |  | 3 | 2026-10-25 | 2026-10-27 | 2026-10-25 | 2026-10-27 | Subcontractor
Wiring | Services | Wiring Rough-in | — |  | 7 | 2026-10-18 | 2026-10-24 | 2026-10-18 | 2026-10-24 | Subcontractor
Wiring | Services | Wiring Testing | — |  | 3 | 2026-10-25 | 2026-10-27 | 2026-10-25 | 2026-10-27 | Subcontractor
External Plaster | Finishes | External Plaster | 128.178 | sqm | 7 | 2026-10-18 | 2026-10-24 | 2026-10-18 | 2026-10-24 | 2 masons + 2 helpers
Internal Plaster | Finishes | Internal Plaster | 265.69 | sqm | 15 | 2026-10-28 | 2026-11-11 | 2026-10-28 | 2026-11-11 | 2 masons + 2 helpers
Floor Tiles | Finishes | Floor Area | 142.412 | sqm | 12 | 2026-11-12 | 2026-11-23 | 2026-11-12 | 2026-11-23 | 2 masons + 2 helpers
Wall Tiles | Finishes | Wall Tiles | — |  | 10 | 2026-11-24 | 2026-12-03 | 2026-11-24 | 2026-12-03 | Subcontractor
Internal Painting | Finishes | Internal Painting | 265.69 | sqm | 8 | 2026-11-24 | 2026-12-01 | 2026-11-24 | 2026-12-01 | 2 painters
Internal Painting | Finishes | Wooden Door Painting | 7.414 | sqm | 1 | 2026-11-24 | 2026-11-24 | 2026-11-24 | 2026-11-24 | 2 painters
Sanitary Fittings | Fittings | Sanitary Fittings | — |  | 5 | 2026-12-04 | 2026-12-08 | 2026-12-04 | 2026-12-08 | Subcontractor
Cleaning | Handover | Cleaning & Handover | — |  | 3 | 2026-12-09 | 2026-12-11 | 2026-12-09 | 2026-12-11 | Subcontractor

## Foundation
FOUNDATION — ACTIVITY SCHEDULE
Activity | Qty | Unit | Duration | Early Start | Early Finish | Late Start | Late Finish | Total Float | Critical | Gang
Excavation | 52.42 | cum | 12 | 2026-07-23 | 2026-08-03 | 2026-07-23 | 2026-08-03 | 0 | CRITICAL | 4 helpers
PCC(1:4:8) | 5.23 | cum | 2 | 2026-08-04 | 2026-08-05 | 2026-08-04 | 2026-08-05 | 0 | CRITICAL | 1 mason + 4 helpers
Footing main bars | 180.95 | kg | 1 | 2026-08-06 | 2026-08-06 | 2026-08-06 | 2026-08-06 | 0 | CRITICAL | 2 bar benders
Footing Cross Reinforcement | 180.95 | kg | 1 | 2026-08-06 | 2026-08-06 | 2026-08-06 | 2026-08-06 | 0 | CRITICAL | 2 bar benders
Pedestal Reinforcement | 134.45 | kg | 1 | 2026-08-06 | 2026-08-06 | 2026-08-06 | 2026-08-06 | 0 | CRITICAL | 2 bar benders
Pedestal Stirrups | 64.69 | kg | 1 | 2026-08-06 | 2026-08-06 | 2026-08-06 | 2026-08-06 | 0 | CRITICAL | 2 bar benders
FDNColumn Main Bars | 169.82 | kg | 1 | 2026-08-06 | 2026-08-06 | 2026-08-06 | 2026-08-06 | 0 | CRITICAL | 2 bar benders
FDNColumn Stirrups | 30.32 | kg | 1 | 2026-08-06 | 2026-08-06 | 2026-08-06 | 2026-08-06 | 0 | CRITICAL | 2 bar benders
Footing Formwork | 18.1 | m² | 1 | 2026-08-07 | 2026-08-07 | 2026-08-07 | 2026-08-07 | 0 | CRITICAL | 2 carpenters
Pedestal Formwork | 8.49 | m² | 1 | 2026-08-07 | 2026-08-07 | 2026-08-07 | 2026-08-07 | 0 | CRITICAL | 2 carpenters
FDNColumn Formwork | 16.21 | m² | 1 | 2026-08-07 | 2026-08-07 | 2026-08-07 | 2026-08-07 | 0 | CRITICAL | 2 carpenters
FDN RCC(M25) | 10.47 | cum | 7 | 2026-08-08 | 2026-08-14 | 2026-08-08 | 2026-08-14 | 0 | CRITICAL | 2 masons + 6 helpers
Pedestal RCC(M25) | 0.844 | cum | 3 | 2026-08-08 | 2026-08-10 | 2026-08-08 | 2026-08-10 | 0 | CRITICAL | 1 mason + 4 helpers
FDNColumn RCC(M25) | 0.651 | cum | 3 | 2026-08-08 | 2026-08-10 | 2026-08-08 | 2026-08-10 | 0 | CRITICAL | 1 mason + 4 helpers
RFR (Returning and Filling) | 38.75 | m³ | 5 | 2026-08-15 | 2026-08-19 | 2026-08-15 | 2026-08-19 | 0 | CRITICAL | 4 helpers
Removal | 17.19 | m³ | 2 | 2026-08-15 | 2026-08-16 | 2026-08-15 | 2026-08-16 | 0 | CRITICAL | 4 helpers

## Plinth Beam
PLINTH BEAM — ACTIVITY SCHEDULE
Activity | Qty | Unit | Duration | Early Start | Early Finish | Late Start | Late Finish | Total Float | Critical | Gang
Beam Main Bars | 991.32 | kg | 5 | 2026-08-20 | 2026-08-24 | 2026-08-20 | 2026-08-24 | 0 | CRITICAL | 2 bar benders
Beam Extra Bars | — | kg | 1 | 2026-08-20 | 2026-08-20 | 2026-08-20 | 2026-08-20 | 0 | CRITICAL | 2 bar benders
Beam Stirrups | 318.25 | kg | 2 | 2026-08-20 | 2026-08-21 | 2026-08-20 | 2026-08-21 | 0 | CRITICAL | 2 bar benders
Beam Formwork | 127.43 | m² | 5 | 2026-08-25 | 2026-08-29 | 2026-08-25 | 2026-08-29 | 0 | CRITICAL | 3 carpenters
Beam RCC(M25) | 11.4 | m³ | 7 | 2026-08-30 | 2026-09-05 | 2026-08-30 | 2026-09-05 | 0 | CRITICAL | 2 masons + 6 helpers

## GF Columns
GF COLUMNS — ACTIVITY SCHEDULE
Activity | Qty | Unit | Duration | Early Start | Early Finish | Late Start | Late Finish | Total Float | Critical | Gang
Column Main Bars | 335.56 | kg | 2 | 2026-09-06 | 2026-09-07 | 2026-09-06 | 2026-09-07 | 0 | CRITICAL | 2 bar benders
Column Stirrups | 94.54 | kg | 1 | 2026-09-06 | 2026-09-06 | 2026-09-06 | 2026-09-06 | 0 | CRITICAL | 2 bar benders
Column Formwork | 31.17 | m² | 2 | 2026-09-08 | 2026-09-09 | 2026-09-08 | 2026-09-09 | 0 | CRITICAL | 2 carpenters
Column RCC(M25) | 1.91 | m³ | 7 | 2026-09-10 | 2026-09-16 | 2026-09-10 | 2026-09-16 | 0 | CRITICAL | 2 masons + 4 helpers

## GF Beams & Slab
GF BEAMS & SLAB — ACTIVITY SCHEDULE
Activity | Qty | Unit | Duration | Early Start | Early Finish | Late Start | Late Finish | Total Float | Critical | Gang
Beam Main Bars | 991.32 | kg | 2 | 2026-09-17 | 2026-09-18 | 2026-09-17 | 2026-09-18 | 0 | CRITICAL | 2 bar benders
Beam Extra Bars | — | kg | 1 | 2026-09-17 | 2026-09-17 | 2026-09-17 | 2026-09-17 | 0 | CRITICAL | 2 bar benders
Beam Stirrups | 318.25 | kg | 1 | 2026-09-17 | 2026-09-17 | 2026-09-17 | 2026-09-17 | 0 | CRITICAL | 2 bar benders
Slab Main Bars | — |  | 1 | 2026-09-17 | 2026-09-17 | 2026-09-17 | 2026-09-17 | 0 | CRITICAL | 3 bar benders
Slab Cross Bars | — |  | 1 | 2026-09-17 | 2026-09-17 | 2026-09-17 | 2026-09-17 | 0 | CRITICAL | 3 bar benders
Beam Formwork | 127.43 | m² | 2 | 2026-09-19 | 2026-09-20 | 2026-09-19 | 2026-09-20 | 0 | CRITICAL | 3 carpenters
Slab Formwork | 39.08 | m² | 1 | 2026-09-19 | 2026-09-19 | 2026-09-19 | 2026-09-19 | 0 | CRITICAL | 3 carpenters
Beam RCC(M25) | 11.4 | m³ | 7 | 2026-09-21 | 2026-09-27 | 2026-09-21 | 2026-09-27 | 0 | CRITICAL | 2 masons + 6 helpers
Slab RCC(M25) | — |  | 1 | 2026-09-21 | 2026-09-21 | 2026-09-21 | 2026-09-21 | 0 | CRITICAL | 3 masons + 8 helpers

## Staircase
STAIRCASE — ACTIVITY SCHEDULE
Activity | Qty | Unit | Duration | Early Start | Early Finish | Late Start | Late Finish | Total Float | Critical | Gang
Beam Main Bars | — |  | 1 | 2026-09-17 | 2026-09-17 | 2026-12-09 | 2026-12-09 | 83 | +83d | 2 bar benders
Beam Formwork | — |  | 1 | 2026-09-18 | 2026-09-18 | 2026-12-10 | 2026-12-10 | 83 | +83d | 3 carpenters
Beam RCC(M25) | — |  | 1 | 2026-09-19 | 2026-09-19 | 2026-12-11 | 2026-12-11 | 83 | +83d | 2 masons + 6 helpers

## Lintel Beams
LINTEL BEAMS — ACTIVITY SCHEDULE
Activity | Qty | Unit | Duration | Early Start | Early Finish | Late Start | Late Finish | Total Float | Critical | Gang
Beam Main Bars | — |  | 1 | 2026-09-28 | 2026-09-28 | 2026-09-28 | 2026-09-28 | 0 | CRITICAL | 2 bar benders
Beam Stirrups | — |  | 1 | 2026-09-28 | 2026-09-28 | 2026-09-28 | 2026-09-28 | 0 | CRITICAL | 2 bar benders
Beam Formwork | — |  | 1 | 2026-09-29 | 2026-09-29 | 2026-09-29 | 2026-09-29 | 0 | CRITICAL | 3 carpenters
Beam RCC(M25) | — |  | 1 | 2026-09-30 | 2026-09-30 | 2026-09-30 | 2026-09-30 | 0 | CRITICAL | 2 masons + 6 helpers

## Walls
WALLS — ACTIVITY SCHEDULE
Activity | Qty | Unit | Duration | Early Start | Early Finish | Late Start | Late Finish | Total Float | Critical | Gang
Full Brick Wall | 41.919 | cum | 17 | 2026-10-01 | 2026-10-17 | 2026-10-01 | 2026-10-17 | 0 | CRITICAL | 2 masons + 4 helpers
Half Brick Wall | — | sqm | 1 | 2026-10-01 | 2026-10-01 | 2026-10-01 | 2026-10-01 | 0 | CRITICAL | 2 masons + 3 helpers

## Subfloor
SUBFLOOR — ACTIVITY SCHEDULE
Activity | Qty | Unit | Duration | Early Start | Early Finish | Late Start | Late Finish | Total Float | Critical | Gang
Subfloor Filling | 28.482 | cum | 5 | 2026-10-18 | 2026-10-22 | 2026-10-30 | 2026-11-03 | 12 | +12d | 4 helpers
Subfloor PCC 1:3:6 | 14.241 | cum | 6 | 2026-10-23 | 2026-10-28 | 2026-11-04 | 2026-11-09 | 12 | +12d | 1 mason + 4 helpers
Subfloor PCC 1:2:4 | 10.681 | cum | 6 | 2026-10-23 | 2026-10-28 | 2026-11-04 | 2026-11-09 | 12 | +12d | 1 mason + 4 helpers
Cement Screed Bed | 2.848 | cum | 2 | 2026-10-29 | 2026-10-30 | 2026-11-10 | 2026-11-11 | 12 | +12d | 2 masons

## Plumbing
PLUMBING — ACTIVITY SCHEDULE
Activity | Qty | Unit | Duration | Early Start | Early Finish | Late Start | Late Finish | Total Float | Critical | Gang
Plumbing Rough-in | — |  | 7 | 2026-10-18 | 2026-10-24 | 2026-10-18 | 2026-10-24 | 0 | CRITICAL | Subcontractor (assumed)
Plumbing Testing | — |  | 3 | 2026-10-25 | 2026-10-27 | 2026-10-25 | 2026-10-27 | 0 | CRITICAL | Subcontractor (assumed)

## Wiring
WIRING — ACTIVITY SCHEDULE
Activity | Qty | Unit | Duration | Early Start | Early Finish | Late Start | Late Finish | Total Float | Critical | Gang
Wiring Rough-in | — |  | 7 | 2026-10-18 | 2026-10-24 | 2026-10-18 | 2026-10-24 | 0 | CRITICAL | Subcontractor (assumed)
Wiring Testing | — |  | 3 | 2026-10-25 | 2026-10-27 | 2026-10-25 | 2026-10-27 | 0 | CRITICAL | Subcontractor (assumed)

## External Plaster
EXTERNAL PLASTER — ACTIVITY SCHEDULE
Activity | Qty | Unit | Duration | Early Start | Early Finish | Late Start | Late Finish | Total Float | Critical | Gang
External Plaster | 128.178 | sqm | 7 | 2026-10-18 | 2026-10-24 | 2026-10-18 | 2026-10-24 | 0 | CRITICAL | 2 masons + 2 helpers

## Internal Plaster
INTERNAL PLASTER — ACTIVITY SCHEDULE
Activity | Qty | Unit | Duration | Early Start | Early Finish | Late Start | Late Finish | Total Float | Critical | Gang
Internal Plaster | 265.69 | sqm | 15 | 2026-10-28 | 2026-11-11 | 2026-10-28 | 2026-11-11 | 0 | CRITICAL | 2 masons + 2 helpers

## Floor Tiles
FLOOR TILES — ACTIVITY SCHEDULE
Activity | Qty | Unit | Duration | Early Start | Early Finish | Late Start | Late Finish | Total Float | Critical | Gang
Floor Area | 142.412 | sqm | 12 | 2026-11-12 | 2026-11-23 | 2026-11-12 | 2026-11-23 | 0 | CRITICAL | 2 masons + 2 helpers

## External Painting
EXTERNAL PAINTING — ACTIVITY SCHEDULE
Activity | Qty | Unit | Duration | Early Start | Early Finish | Late Start | Late Finish | Total Float | Critical | Gang
External Painting | 128.178 | sqm | 4 | 2026-10-25 | 2026-10-28 | 2026-12-08 | 2026-12-11 | 44 | +44d | 2 painters

## Wall Tiles
WALL TILES — ACTIVITY SCHEDULE
Activity | Qty | Unit | Duration | Early Start | Early Finish | Late Start | Late Finish | Total Float | Critical | Gang
Wall Tiles | — |  | 10 | 2026-11-24 | 2026-12-03 | 2026-11-24 | 2026-12-03 | 0 | CRITICAL | Subcontractor (assumed)

## Internal Painting
INTERNAL PAINTING — ACTIVITY SCHEDULE
Activity | Qty | Unit | Duration | Early Start | Early Finish | Late Start | Late Finish | Total Float | Critical | Gang
Internal Painting | 265.69 | sqm | 8 | 2026-11-24 | 2026-12-01 | 2026-11-24 | 2026-12-01 | 0 | CRITICAL | 2 painters
Wooden Door Painting | 7.414 | sqm | 1 | 2026-11-24 | 2026-11-24 | 2026-11-24 | 2026-11-24 | 0 | CRITICAL | 2 painters

## Sanitary Fittings
SANITARY FITTINGS — ACTIVITY SCHEDULE
Activity | Qty | Unit | Duration | Early Start | Early Finish | Late Start | Late Finish | Total Float | Critical | Gang
Sanitary Fittings | — |  | 5 | 2026-12-04 | 2026-12-08 | 2026-12-04 | 2026-12-08 | 0 | CRITICAL | Subcontractor (assumed)

## Light Fittings
LIGHT FITTINGS — ACTIVITY SCHEDULE
Activity | Qty | Unit | Duration | Early Start | Early Finish | Late Start | Late Finish | Total Float | Critical | Gang
Light Fittings | — |  | 5 | 2026-12-02 | 2026-12-06 | 2026-12-04 | 2026-12-08 | 2 | +2d | Subcontractor (assumed)

## Cleaning
CLEANING — ACTIVITY SCHEDULE
Activity | Qty | Unit | Duration | Early Start | Early Finish | Late Start | Late Finish | Total Float | Critical | Gang
Cleaning & Handover | — |  | 3 | 2026-12-09 | 2026-12-11 | 2026-12-09 | 2026-12-11 | 0 | CRITICAL | Subcontractor (assumed)

## Productivity Used
PRODUCTIVITY CONSTANTS (NBC/IS Standards)
Activity | Rate | Unit | Min Days (NBC) | Gang
Excavation | 4.5 | cum | 1 | 4 helpers
PCC(1:4:8) | 3 | cum | 1 | 1 mason + 4 helpers
FDN RCC(M25) | 2.5 | cum | 7 | 2 masons + 6 helpers
Pedestal RCC(M25) | 2 | cum | 3 | 1 mason + 4 helpers
FDNColumn RCC(M25) | 2 | cum | 3 | 1 mason + 4 helpers
Footing main bars | 200 | kg | 1 | 2 bar benders
Footing Cross Reinforcement | 200 | kg | 1 | 2 bar benders
Pedestal Reinforcement | 200 | kg | 1 | 2 bar benders
Pedestal Stirrups | 150 | kg | 1 | 2 bar benders
FDNColumn Main Bars | 200 | kg | 1 | 2 bar benders
FDNColumn Stirrups | 150 | kg | 1 | 2 bar benders
Footing Formwork | 25 | sqm | 1 | 2 carpenters
Pedestal Formwork | 20 | sqm | 1 | 2 carpenters
FDNColumn Formwork | 20 | sqm | 1 | 2 carpenters
RFR (Returning and Filling) | 8 | cum | 1 | 4 helpers
Removal | 10 | cum | 1 | 4 helpers
Beam RCC(M25) | 2 | cum | 7 | 2 masons + 6 helpers
Beam Formwork | 30 | sqm | 1 | 3 carpenters
Beam Main Bars | 220 | kg | 1 | 2 bar benders
Beam Extra Bars | 220 | kg | 1 | 2 bar benders
Beam Stirrups | 180 | kg | 1 | 2 bar benders
Beam Total Steel | 220 | kg | 1 | 2 bar benders
Slab RCC(M25) | 3.5 | cum | 14 | 3 masons + 8 helpers
Slab Main Bars | 250 | kg | 1 | 3 bar benders
Slab Cross Bars | 250 | kg | 1 | 3 bar benders
Slab Formwork | 40 | sqm | 1 | 3 carpenters
Slab Total Steel | 250 | kg | 1 | 3 bar benders
Column RCC(M25) | 1.5 | cum | 7 | 2 masons + 4 helpers
Column Main Bars | 200 | kg | 1 | 2 bar benders
Column Stirrups | 150 | kg | 1 | 2 bar benders
Column Formwork | 22 | sqm | 1 | 2 carpenters
Column Total Steel | 200 | kg | 1 | 2 bar benders
Full Brick Wall | 2.5 | cum | 3 | 2 masons + 4 helpers
Half Brick Wall | 3 | cum | 2 | 2 masons + 3 helpers
Subfloor Filling | 6 | cum | 1 | 4 helpers
Subfloor PCC 1:3:6 | 2.5 | cum | 1 | 1 mason + 4 helpers
Subfloor PCC 1:2:4 | 2 | cum | 1 | 1 mason + 4 helpers
Cement Screed Bed | 15 | sqm | 2 | 2 masons
Floor Area | 12 | sqm | 1 | 2 masons + 2 helpers
Wooden Door Shutter | 4 | sqm | 1 | 2 carpenters
Wooden Door Frame | 0.05 | cum | 1 | 2 carpenters
UPVC Toilet Door | 4 | sqm | 1 | 2 carpenters
UPVC Windows | 8 | sqm | 1 | 2 carpenters
UPVC Ventilators | 6 | sqm | 1 | 2 carpenters
External Plaster | 20 | sqm | 1 | 2 masons + 2 helpers
Internal Plaster | 18 | sqm | 1 | 2 masons + 2 helpers
External Painting | 40 | sqm | 1 | 2 painters
Internal Painting | 35 | sqm | 1 | 2 painters
Wooden Door Painting | 12 | sqm | 1 | 2 painters