## Summary
LABOUR REQUIREMENT SUMMARY — ALL FLOORS
Floor / Module | Item | Work Unit | Work Qty | Labour Days (days)
Project ID: 6a5f18ab1bbc14bb70784e2e ¦ Generated: 2026-07-27 13:21 UTC
|  |  |  | Helper | Mason | Mixer Operator | Bar Bender | Carpenter | Tile Fixer | Painter
GROUND FLOOR
Foundation
| Excavation | cum | 60.71 | 30.355
| PCC(1:4:8) | cum | 3.03 | 7.4841
| PCC(1:4:8) | cum | 3.03 |  | 0.303
| FDN RCC(M25) | cum | 11.07 | 33.6528
| FDN RCC(M25) | cum | 11.07 |  | 1.8819
| FDN RCC(M25) | cum | 11.07 |  |  | 0.7749
| FDNColumn RCC(M25) | cum | 0.973 | 2.9579
| FDNColumn RCC(M25) | cum | 0.973 |  | 0.1654
| FDNColumn RCC(M25) | cum | 0.973 |  |  | 0.0681
| Footing main bars | kg | 180.95 |  |  |  | 1.14
| Footing Cross Reinforcement | kg | 180.95 |  |  |  | 1.14
| FDNColumn Main Bars | kg | 224.89 |  |  |  | 1.4168
| FDNColumn Stirrups | kg | 40.93 |  |  |  | 0.2579
| Footing Formwork | m² | 18.1 |  |  |  |  | 2.353
| Footing Formwork | m² | 18.1 | 2.353
| FDNColumn Formwork | m² | 16.21 |  |  |  |  | 2.1073
| FDNColumn Formwork | m² | 16.21 | 2.1073
| RFR (Returning and Filling) | m³ | 50.2
| Removal | m³ | 15.07
|  |  | Total | 78.9101 | 2.3503 | 0.843 | 3.9547 | 4.4603
Plinth Beam
| Beam RCC(M25) | m³ | 11.51 | 46.04
| Beam RCC(M25) | m³ | 11.51 |  | 2.302
| Beam RCC(M25) | m³ | 11.51 |  |  | 0.8057
| Beam Formwork | m² | 128.54 |  |  |  |  | 38.562
| Beam Formwork | m² | 128.54 | 25.708
| Beam Main Bars | kg | 1006.6 |  |  |  | 6.5429
| Beam Extra Bars | kg | 0 |  |  |  | 0
| Beam Stirrups | kg | 318.97 |  |  |  | 2.0733
| Beam Total Steel | kg | 1325.57
|  |  | Total | 71.748 | 2.302 | 0.8057 | 8.6162 | 38.562
Beams
| Beam RCC(M25) | cum | 2.28 | 9.12
| Beam RCC(M25) | cum | 2.28 |  | 0.456
| Beam RCC(M25) | cum | 2.28 |  |  | 0.1596
| Beam Formwork | Sqm | 34.28 |  |  |  |  | 10.284
| Beam Formwork | Sqm | 34.28 | 6.856
| Beam Main Bars | kg | 358.29 |  |  |  | 2.3289
| Beam Extra Bars | kg | 208.43 |  |  |  | 1.3548
| Beam Stirrups | kg | 138.6 |  |  |  | 0.9009
| Beam Total Steel | kg | 705.32
|  |  | Total | 15.976 | 0.456 | 0.1596 | 4.5846 | 10.284
Slab
| Slab RCC (M25) | m³ | 1.605 | 5.5694
| Slab RCC (M25) | m³ | 1.605 |  | 0.3852
| Slab RCC (M25) | m³ | 1.605 |  |  | 0.1124
| Slab Main Bars SS | kg | 57.84 |  |  |  | 0.376
| Slab Dist Bars LS | kg | 36.41 |  |  |  | 0.2367
| Slab Top Dist Bars | kg | 16.16 |  |  |  | 0.105
| Slab Total Steel | kg | 110.41
| Slab Total Steel | qntl | 1.104
| Slab Formwork | m² | 42.91 |  |  |  |  | 9.8693
| Slab Formwork | m² | 42.91 | 8.582
|  |  | Total | 14.1514 | 0.3852 | 0.1124 | 0.7177 | 9.8693
Columns
| Column RCC(M25) | m³ | 2.57 | 11.7449
| Column RCC(M25) | m³ | 2.57 |  | 0.5911
| Column RCC(M25) | m³ | 2.57 |  |  | 0.1799
| Column Main Bars | kg | 378.18 |  |  |  | 2.3825
| Column Stirrups | kg | 121.72 |  |  |  | 0.7668
| Column Formwork | m² | 41.08 |  |  |  |  | 10.27
| Column Formwork | m² | 41.08 | 8.216
|  |  | Total | 19.9609 | 0.5911 | 0.1799 | 3.1493 | 10.27
Lintel Beams
| Beam RCC(M25) | m³ | 4.76 | 19.04
| Beam RCC(M25) | m³ | 4.76 |  | 0.952
| Beam RCC(M25) | m³ | 4.76 |  |  | 0.3332
| Beam Formwork | m² | 62.34 |  |  |  |  | 18.702
| Beam Formwork | m² | 62.34 | 12.468
| Beam Main Bars | kg | 337.24 |  |  |  | 2.1921
| Beam Stirrups | kg | 230.54 |  |  |  | 1.4985
| total reinforcement | kg | 567.78
|  |  | Total | 31.508 | 0.952 | 0.3332 | 3.6906 | 18.702
Walls / Floor / Doors / Finishes
| Wooden Door Shutter | sqm | 6.175 |  |  |  |  | 1.235
| Wooden Door Shutter | sqm | 6.175 | 0.6175
| Wooden Door Frame | cum | 0.113 |  |  |  |  | 0.0848
| Wooden Door Frame | cum | 0.113 | 0.0424
| UPVC Toilet Door | sqm | 6.501 |  |  |  |  | 2.2753
| UPVC Toilet Door | sqm | 6.501 | 1.1702
| UPVC Windows | sqm | 19.879 |  |  |  |  | 9.9395
| UPVC Windows | sqm | 19.879 | 4.9698
| UPVC Ventilators | sqm | 0.744 |  |  |  |  | 0.279
| UPVC Ventilators | sqm | 0.744 | 0.186
| Full Brick Wall | cum | 41.012 | 79.1532
| Full Brick Wall | cum | 41.012 |  | 40.1918
| Half Brick Wall | sqm | 0 | 0
| Half Brick Wall | sqm | 0 |  | 0
| Floor Area | sqm | 142.587 | 78.4228
| Floor Area | sqm | 142.587 |  | 78.4228
| Floor Area | sqm | 142.587 | [5 empty] | 21.388
| External Plaster | sqm | 128.178 | 21.7903
| External Plaster | sqm | 128.178 |  | 14.0996
| Internal Plaster | sqm | 261.748 | 34.0272
| Internal Plaster | sqm | 261.748 |  | 20.9398
| External Painting | sqm | 128.178 | 5.768
| External Painting | sqm | 128.178 | [6 empty] | 7.0498
| Internal Painting | sqm | 261.748 | 9.1612
| Internal Painting | sqm | 261.748 | [6 empty] | 11.7787
| Wooden Door Painting | sqm | 7.41 | 0.3705
| Wooden Door Painting | sqm | 7.41 | [6 empty] | 0.8151
| Subfloor Filling | cum | 28.517 | 57.034
| Subfloor PCC 1:3:6 | cum | 14.259 | 35.2197
| Subfloor PCC 1:3:6 | cum | 14.259 |  | 1.4259
| Subfloor PCC 1:2:4 | cum | 10.694 | 26.4142
| Subfloor PCC 1:2:4 | cum | 10.694 |  | 1.0694
| Cement Screed Bed | cum | 2.852 | 0.5704
| Cement Screed Bed | cum | 2.852 |  | 0.5704
|  |  | Total | 354.9174 | 156.7197 |  |  | 13.8136 | 21.388 | 19.6436
FIRST FLOOR
Beams
| Beam RCC(M25) | cum | 2.4 | 9.6
| Beam RCC(M25) | cum | 2.4 |  | 0.48
| Beam RCC(M25) | cum | 2.4 |  |  | 0.168
| Beam Formwork | Sqm | 35.99 |  |  |  |  | 10.797
| Beam Formwork | Sqm | 35.99 | 7.198
| Beam Main Bars | kg | 382.7 |  |  |  | 2.4876
| Beam Extra Bars | kg | 224.71 |  |  |  | 1.4606
| Beam Stirrups | kg | 144.92 |  |  |  | 0.942
| Beam Total Steel | kg | 752.33
|  |  | Total | 16.798 | 0.48 | 0.168 | 4.8902 | 10.797
Slab
| Slab RCC (M25) | m³ | 4.965 | 17.2286
| Slab RCC (M25) | m³ | 4.965 |  | 1.1916
| Slab RCC (M25) | m³ | 4.965 |  |  | 0.3476
| Slab Main Bars SS | kg | 172.92 |  |  |  | 1.124
| Slab Dist Bars LS | kg | 148.95 |  |  |  | 0.9682
| Slab Top Dist Bars | kg | 74.88 |  |  |  | 0.4867
| Slab Total Steel | kg | 396.75
| Slab Total Steel | qntl | 3.967
| Slab Formwork | m² | 39.08 |  |  |  |  | 8.9884
| Slab Formwork | m² | 39.08 | 7.816
|  |  | Total | 25.0446 | 1.1916 | 0.3476 | 2.5789 | 8.9884
Columns
| Column RCC(M25) | m³ | 1.91 | 8.7287
| Column RCC(M25) | m³ | 1.91 |  | 0.4393
| Column RCC(M25) | m³ | 1.91 |  |  | 0.1337
| Column Main Bars | kg | 197.14 |  |  |  | 1.242
| Column Stirrups | kg | 94.54 |  |  |  | 0.5956
| Column Formwork | m² | 31.17 |  |  |  |  | 7.7925
| Column Formwork | m² | 31.17 | 6.234
|  |  | Total | 14.9627 | 0.4393 | 0.1337 | 1.8376 | 7.7925
Lintel Beams
| Beam RCC(M25) | m³ | 1.51 | 6.04
| Beam RCC(M25) | m³ | 1.51 |  | 0.302
| Beam RCC(M25) | m³ | 1.51 |  |  | 0.1057
| Beam Formwork | m² | 19.82 |  |  |  |  | 5.946
| Beam Formwork | m² | 19.82 | 3.964
| Beam Main Bars | kg | 106.76 |  |  |  | 0.6939
| Beam Stirrups | kg | 73.63 |  |  |  | 0.4786
| total reinforcement | kg | 180.39
|  |  | Total | 10.004 | 0.302 | 0.1057 | 1.1725 | 5.946
Walls / Floor / Doors / Finishes
| Wooden Door Shutter | sqm | 1.95 |  |  |  |  | 0.39
| Wooden Door Shutter | sqm | 1.95 | 0.195
| Wooden Door Frame | cum | 0.037 |  |  |  |  | 0.0277
| Wooden Door Frame | cum | 0.037 | 0.0139
| UPVC Toilet Door | sqm | 1.625 |  |  |  |  | 0.5687
| UPVC Toilet Door | sqm | 1.625 | 0.2925
| UPVC Windows | sqm | 2.786 |  |  |  |  | 1.393
| UPVC Windows | sqm | 2.786 | 0.6965
| UPVC Ventilators | sqm | 0.558 |  |  |  |  | 0.2093
| UPVC Ventilators | sqm | 0.558 | 0.1395
| Full Brick Wall | cum | 11.843 | 22.857
| Full Brick Wall | cum | 11.843 |  | 11.6061
| Half Brick Wall | sqm | 8.885 | 2.2212
| Half Brick Wall | sqm | 8.885 |  | 1.155
| Floor Area | sqm | 25.135 | 13.8243
| Floor Area | sqm | 25.135 |  | 13.8243
| Floor Area | sqm | 25.135 | [5 empty] | 3.7702
| External Plaster | sqm | 52.454 | 8.9172
| External Plaster | sqm | 52.454 |  | 5.7699
| Internal Plaster | sqm | 75.212 | 9.7776
| Internal Plaster | sqm | 75.212 |  | 6.017
| External Painting | sqm | 52.454 | 2.3604
| External Painting | sqm | 52.454 | [6 empty] | 2.885
| Internal Painting | sqm | 75.212 | 2.6324
| Internal Painting | sqm | 75.212 | [6 empty] | 3.3845
| Wooden Door Painting | sqm | 2.339 | 0.1169
| Wooden Door Painting | sqm | 2.339 | [6 empty] | 0.2573
| Subfloor Filling | cum | 5.027 | 10.054
| Subfloor PCC 1:3:6 | cum | 2.514 | 6.2096
| Subfloor PCC 1:3:6 | cum | 2.514 |  | 0.2514
| Subfloor PCC 1:2:4 | cum | 1.885 | 4.656
| Subfloor PCC 1:2:4 | cum | 1.885 |  | 0.1885
| Cement Screed Bed | cum | 0.503 | 0.1006
| Cement Screed Bed | cum | 0.503 |  | 0.1006
|  |  | Total | 85.0646 | 38.9128 |  |  | 2.5887 | 3.7702 | 6.5268
|  |  | GRAND TOTAL | 739.0457 | 205.082 | 3.1888 | 35.1923 | 142.0738 | 25.1582 | 26.1704

## Constants Used
LABOUR CONSTANTS — 2026-07-27 13:21 UTC
Work Item | Work Unit | Labour Type | Constant | Unit | Source
Excavation | cum | Helper | 0.5 | days per cum | default
PCC(1:4:8) | cum | Helper | 2.47 | days per cum | default
PCC(1:4:8) | cum | Mason | 0.1 | days per cum | default
PCC(1:3:6) | cum | Helper | 2.47 | days per cum | default
PCC(1:3:6) | cum | Mason | 0.1 | days per cum | default
FDN RCC(M25) | cum | Helper | 3.04 | days per cum | default
FDN RCC(M25) | cum | Mason | 0.17 | days per cum | default
FDN RCC(M25) | cum | Mixer Operator | 0.07 | days per cum | default
Pedestal RCC(M25) | cum | Helper | 3.04 | days per cum | default
Pedestal RCC(M25) | cum | Mason | 0.17 | days per cum | default
Pedestal RCC(M25) | cum | Mixer Operator | 0.07 | days per cum | default
FDNColumn RCC(M25) | cum | Helper | 3.04 | days per cum | default
FDNColumn RCC(M25) | cum | Mason | 0.17 | days per cum | default
FDNColumn RCC(M25) | cum | Mixer Operator | 0.07 | days per cum | default
Footing main bars | quintal | Bar Bender | 0.63 | days per quintal | default
Footing Cross Reinforcement | quintal | Bar Bender | 0.63 | days per quintal | default
Pedestal Reinforcement | quintal | Bar Bender | 0.63 | days per quintal | default
Pedestal Stirrups | quintal | Bar Bender | 0.63 | days per quintal | default
FDNColumn Main Bars | quintal | Bar Bender | 0.63 | days per quintal | default
FDNColumn Stirrups | quintal | Bar Bender | 0.63 | days per quintal | default
Footing Formwork | sqm | Carpenter | 0.13 | days per sqm | default
Footing Formwork | sqm | Helper | 0.13 | days per sqm | default
Pedestal Formwork | sqm | Carpenter | 0.13 | days per sqm | default
Pedestal Formwork | sqm | Helper | 0.13 | days per sqm | default
FDNColumn Formwork | sqm | Carpenter | 0.13 | days per sqm | default
FDNColumn Formwork | sqm | Helper | 0.13 | days per sqm | default
Beam RCC(M25) | cum | Helper | 4 | days per cum | default
Beam RCC(M25) | cum | Mason | 0.2 | days per cum | default
Beam RCC(M25) | cum | Mixer Operator | 0.07 | days per cum | default
Beam Formwork | sqm | Carpenter | 0.3 | days per sqm | default
Beam Formwork | sqm | Helper | 0.2 | days per sqm | default
Beam Main Bars | quintal | Bar Bender | 0.65 | days per quintal | default
Beam Extra Bars | quintal | Bar Bender | 0.65 | days per quintal | default
Beam Stirrups | quintal | Bar Bender | 0.65 | days per quintal | default
Column RCC(M25) | cum | Helper | 4.57 | days per cum | default
Column RCC(M25) | cum | Mason | 0.23 | days per cum | default
Column RCC(M25) | cum | Mixer Operator | 0.07 | days per cum | default
Column Formwork | sqm | Carpenter | 0.25 | days per sqm | default
Column Formwork | sqm | Helper | 0.2 | days per sqm | default
Column Main Bars | quintal | Bar Bender | 0.63 | days per quintal | default
Column Stirrups | quintal | Bar Bender | 0.63 | days per quintal | default
Slab RCC (M25) | cum | Helper | 3.47 | days per cum | default
Slab RCC (M25) | cum | Mason | 0.24 | days per cum | default
Slab RCC (M25) | cum | Mixer Operator | 0.07 | days per cum | default
Slab Formwork | sqm | Carpenter | 0.23 | days per sqm | default
Slab Formwork | sqm | Helper | 0.2 | days per sqm | default
Slab Main Bars SS | kg | Bar Bender | 0.0065 | days per kg | default
Slab Dist Bars LS | kg | Bar Bender | 0.0065 | days per kg | default
Slab Top Dist Bars | kg | Bar Bender | 0.0065 | days per kg | default
Wooden Door Shutter | Nos | Carpenter | 0.2 | days per Nos | default
Wooden Door Shutter | Nos | Helper | 0.1 | days per Nos | default
Wooden Door Frame | cum | Carpenter | 0.75 | days per cum | default
Wooden Door Frame | cum | Helper | 0.375 | days per cum | default
UPVC Toilet Door | Nos | Carpenter | 0.35 | days per Nos | default
UPVC Toilet Door | Nos | Helper | 0.18 | days per Nos | default
UPVC Windows | Nos | Carpenter | 0.5 | days per Nos | default
UPVC Windows | Nos | Helper | 0.25 | days per Nos | default
UPVC Ventilators | Nos | Carpenter | 0.375 | days per Nos | default
UPVC Ventilators | Nos | Helper | 0.25 | days per Nos | default
Full Brick Wall | cum | Helper | 1.93 | days per cum | default
Full Brick Wall | cum | Mason | 0.98 | days per cum | default
Half Brick Wall | sqm | Helper | 0.25 | days per sqm | default
Half Brick Wall | sqm | Mason | 0.13 | days per sqm | default
Floor Area | sqm | Helper | 0.55 | days per sqm | default
Floor Area | sqm | Mason | 0.55 | days per sqm | default
Floor Area | sqm | Tile Fixer | 0.15 | days per sqm | default
Internal Plaster | sqm | Helper | 0.13 | days per sqm | default
Internal Plaster | sqm | Mason | 0.08 | days per sqm | default
External Plaster | sqm | Helper | 0.17 | days per sqm | default
External Plaster | sqm | Mason | 0.11 | days per sqm | default
External Painting | sqm | Helper | 0.045 | days per sqm | default
External Painting | sqm | Painter | 0.055 | days per sqm | default
Internal Painting | sqm | Helper | 0.035 | days per sqm | default
Internal Painting | sqm | Painter | 0.045 | days per sqm | default
Wooden Door Painting | sqm | Helper | 0.05 | days per sqm | default
Wooden Door Painting | sqm | Painter | 0.11 | days per sqm | default
Subfloor Filling | cum | Helper | 2 | days per cum | default
Subfloor PCC 1:3:6 | cum | Helper | 2.47 | days per cum | default
Subfloor PCC 1:3:6 | cum | Mason | 0.1 | days per cum | default
Subfloor PCC 1:2:4 | cum | Helper | 2.47 | days per cum | default
Subfloor PCC 1:2:4 | cum | Mason | 0.1 | days per cum | default
Cement Screed Bed | sqm | Helper | 0.2 | days per sqm | default
Cement Screed Bed | sqm | Mason | 0.2 | days per sqm | default