## Summary
PROJECT CONSTRUCTION SCHEDULE — SUMMARY
Project ID: 6a7318caed9754502410d07d ¦ Start: 06 Aug 2026 ¦ End: 10 Jan 2027 ¦ Duration: 158 days
⚠ Target end date (20 Nov 2026) not achievable. Minimum construction time per NBC/IS standards is 158 days (ending 10 Jan 2027). Schedule prepared on minimum required duration.
Stage | Phase | Start | Finish | Duration | Float | Critical | Predecessors | Remarks
Foundation | Substructure | 2026-08-06 | 2026-09-01 | 27 | 0 | CRITICAL | —
Plinth Beam | Substructure | 2026-09-02 | 2026-09-19 | 18 | 0 | CRITICAL | Foundation
GF Columns | Superstructure | 2026-09-20 | 2026-09-30 | 11 | 0 | CRITICAL | Plinth Beam
GF Beams & Slab | Superstructure | 2026-10-01 | 2026-10-16 | 16 | 0 | CRITICAL | GF Columns | Monolithic cast with slab
Staircase | Superstructure | 2026-10-01 | 2026-10-03 | 3 | 99 | Normal | GF Columns | Can start 99d later
Lintel Beams | Superstructure | 2026-10-17 | 2026-10-28 | 12 | 0 | CRITICAL | GF Beams & Slab
Walls | Masonry | 2026-10-29 | 2026-11-15 | 18 | 0 | CRITICAL | Lintel Beams
Subfloor | Masonry | 2026-11-16 | 2026-11-28 | 13 | 12 | Normal | Walls | Can start 12d later
Plumbing | Services | 2026-11-16 | 2026-11-25 | 10 | 0 | CRITICAL | Walls | Assumed — subcontractor
Wiring | Services | 2026-11-16 | 2026-11-25 | 10 | 0 | CRITICAL | Walls | Assumed — subcontractor
External Plaster | Finishes | 2026-11-16 | 2026-11-22 | 7 | 0 | CRITICAL | Walls
Internal Plaster | Finishes | 2026-11-26 | 2026-12-10 | 15 | 0 | CRITICAL | Plumbing, Wiring
Floor Tiles | Finishes | 2026-12-11 | 2026-12-23 | 13 | 0 | CRITICAL | Internal Plaster, Subfloor
External Painting | Finishes | 2026-11-23 | 2026-11-26 | 4 | 45 | Normal | External Plaster | Can start 45d later
Wall Tiles | Finishes | 2026-12-24 | 2027-01-02 | 10 | 0 | CRITICAL | Floor Tiles
Internal Painting | Finishes | 2026-12-24 | 2026-12-31 | 8 | 0 | CRITICAL | Floor Tiles
Sanitary Fittings | Fittings | 2027-01-03 | 2027-01-07 | 5 | 0 | CRITICAL | Wall Tiles
Light Fittings | Fittings | 2027-01-01 | 2027-01-05 | 5 | 2 | Normal | Internal Painting | Can start 2d later
Cleaning | Handover | 2027-01-08 | 2027-01-10 | 3 | 0 | CRITICAL | Sanitary Fittings, Light Fittings

## Gantt Chart
BAR CHART PROGRAMME
Stage | Phase | Dur | Start | Finish | Bar (weeks →)
[6 empty] | W1 06 Aug | W2 13 Aug | W3 20 Aug | W4 27 Aug | W5 03 Sep | W6 10 Sep | W7 17 Sep | W8 24 Sep | W9 01 Oct | W10 08 Oct | W11 15 Oct | W12 22 Oct | W13 29 Oct | W14 05 Nov | W15 12 Nov | W16 19 Nov | W17 26 Nov | W18 03 Dec | W19 10 Dec | W20 17 Dec | W21 24 Dec | W22 31 Dec | W23 07 Jan | W24 14 Jan
— SUBSTRUCTURE —
Foundation | Substructure | 27 | 2026-08-06 | 2026-09-01 |  | █ | █ | █ | █
Plinth Beam | Substructure | 18 | 2026-09-02 | 2026-09-19 | [5 empty] | █ | █ | █
— SUPERSTRUCTURE —
GF Columns | Superstructure | 11 | 2026-09-20 | 2026-09-30 | [8 empty] | █
GF Beams & Slab | Superstructure | 16 | 2026-10-01 | 2026-10-16 | [9 empty] | █ | █ | █
Staircase | Superstructure | 3 | 2026-10-01 | 2026-10-03 | [9 empty] | █ | ░ | ░ | ░ | ░ | ░ | ░ | ░ | ░ | ░ | ░ | ░ | ░ | ░ | ░
Lintel Beams | Superstructure | 12 | 2026-10-17 | 2026-10-28 | [12 empty] | █
— MASONRY —
Walls | Masonry | 18 | 2026-10-29 | 2026-11-15 | [13 empty] | █ | █ | █
Subfloor | Masonry | 13 | 2026-11-16 | 2026-11-28 | [16 empty] | █ | █ | ░ | ░
— SERVICES —
Plumbing | Services | 10 | 2026-11-16 | 2026-11-25 | [16 empty] | █
Wiring | Services | 10 | 2026-11-16 | 2026-11-25 | [16 empty] | █
— FINISHES —
External Plaster | Finishes | 7 | 2026-11-16 | 2026-11-22 | [16 empty] | █
Internal Plaster | Finishes | 15 | 2026-11-26 | 2026-12-10 | [17 empty] | █ | █ | █
Floor Tiles | Finishes | 13 | 2026-12-11 | 2026-12-23 | [20 empty] | █
External Painting | Finishes | 4 | 2026-11-23 | 2026-11-26 | [17 empty] | █ | ░ | ░ | ░ | ░ | ░ | ░
Wall Tiles | Finishes | 10 | 2026-12-24 | 2027-01-02 | [21 empty] | █ | █
Internal Painting | Finishes | 8 | 2026-12-24 | 2026-12-31 | [21 empty] | █ | █
— FITTINGS —
Sanitary Fittings | Fittings | 5 | 2027-01-03 | 2027-01-07 | [23 empty] | █
Light Fittings | Fittings | 5 | 2027-01-01 | 2027-01-05 | [23 empty] | ░
— HANDOVER —
Cleaning | Handover | 3 | 2027-01-08 | 2027-01-10
Legend: █ = Activity duration ░ = Total float Red = Critical Phase colours as shown above

## Critical Path
CRITICAL PATH ACTIVITIES (Total Float = 0)
Stage | Phase | Activity | Qty | Unit | Duration | Early Start | Early Finish | Late Start | Late Finish | Gang
Foundation | Substructure | Excavation | 49.91 | cum | 12 | 2026-08-06 | 2026-08-17 | 2026-08-06 | 2026-08-17 | 4 helpers
Foundation | Substructure | PCC(1:4:8) | 2.49 | cum | 1 | 2026-08-18 | 2026-08-18 | 2026-08-18 | 2026-08-18 | 1 mason + 4 helpers
Foundation | Substructure | Footing main bars | 180.95 | kg | 1 | 2026-08-19 | 2026-08-19 | 2026-08-19 | 2026-08-19 | 2 bar benders
Foundation | Substructure | Footing Cross Reinforcement | 180.95 | kg | 1 | 2026-08-19 | 2026-08-19 | 2026-08-19 | 2026-08-19 | 2 bar benders
Foundation | Substructure | Pedestal Reinforcement | 145.23 | kg | 1 | 2026-08-19 | 2026-08-19 | 2026-08-19 | 2026-08-19 | 2 bar benders
Foundation | Substructure | Pedestal Stirrups | 75.59 | kg | 1 | 2026-08-19 | 2026-08-19 | 2026-08-19 | 2026-08-19 | 2 bar benders
Foundation | Substructure | FDNColumn Main Bars | 182.28 | kg | 1 | 2026-08-19 | 2026-08-19 | 2026-08-19 | 2026-08-19 | 2 bar benders
Foundation | Substructure | FDNColumn Stirrups | 31.73 | kg | 1 | 2026-08-19 | 2026-08-19 | 2026-08-19 | 2026-08-19 | 2 bar benders
Foundation | Substructure | Footing Formwork | 18.1 | m² | 1 | 2026-08-20 | 2026-08-20 | 2026-08-20 | 2026-08-20 | 2 carpenters
Foundation | Substructure | Pedestal Formwork | 9.87 | m² | 1 | 2026-08-20 | 2026-08-20 | 2026-08-20 | 2026-08-20 | 2 carpenters
Foundation | Substructure | FDNColumn Formwork | 16.86 | m² | 1 | 2026-08-20 | 2026-08-20 | 2026-08-20 | 2026-08-20 | 2 carpenters
Foundation | Substructure | FDN RCC(M25) | 10.66 | cum | 7 | 2026-08-21 | 2026-08-27 | 2026-08-21 | 2026-08-27 | 2 masons + 6 helpers
Foundation | Substructure | Pedestal RCC(M25) | 1.169 | cum | 3 | 2026-08-21 | 2026-08-23 | 2026-08-21 | 2026-08-23 | 1 mason + 4 helpers
Foundation | Substructure | FDNColumn RCC(M25) | 0.695 | cum | 3 | 2026-08-21 | 2026-08-23 | 2026-08-21 | 2026-08-23 | 1 mason + 4 helpers
Foundation | Substructure | RFR (Returning and Filling) | 38.39 | m³ | 5 | 2026-08-28 | 2026-09-01 | 2026-08-28 | 2026-09-01 | 4 helpers
Foundation | Substructure | Removal | 15.01 | m³ | 2 | 2026-08-28 | 2026-08-29 | 2026-08-28 | 2026-08-29 | 4 helpers
Plinth Beam | Substructure | Beam Main Bars | 1130.18 | kg | 6 | 2026-09-02 | 2026-09-07 | 2026-09-02 | 2026-09-07 | 2 bar benders
Plinth Beam | Substructure | Beam Extra Bars | 7.01 | kg | 1 | 2026-09-02 | 2026-09-02 | 2026-09-02 | 2026-09-02 | 2 bar benders
Plinth Beam | Substructure | Beam Stirrups | 380.22 | kg | 3 | 2026-09-02 | 2026-09-04 | 2026-09-02 | 2026-09-04 | 2 bar benders
Plinth Beam | Substructure | Beam Formwork | 147.22 | m² | 5 | 2026-09-08 | 2026-09-12 | 2026-09-08 | 2026-09-12 | 3 carpenters
Plinth Beam | Substructure | Beam RCC(M25) | 13.17 | m³ | 7 | 2026-09-13 | 2026-09-19 | 2026-09-13 | 2026-09-19 | 2 masons + 6 helpers
GF Columns | Superstructure | Column Main Bars | 363.96 | kg | 2 | 2026-09-20 | 2026-09-21 | 2026-09-20 | 2026-09-21 | 2 bar benders
GF Columns | Superstructure | Column Stirrups | 101.14 | kg | 1 | 2026-09-20 | 2026-09-20 | 2026-09-20 | 2026-09-20 | 2 bar benders
GF Columns | Superstructure | Column Formwork | 34.42 | m² | 2 | 2026-09-22 | 2026-09-23 | 2026-09-22 | 2026-09-23 | 2 carpenters
GF Columns | Superstructure | Column RCC(M25) | 2.11 | m³ | 7 | 2026-09-24 | 2026-09-30 | 2026-09-24 | 2026-09-30 | 2 masons + 4 helpers
GF Beams & Slab | Superstructure | Beam Main Bars | 1130.18 | kg | 5 | 2026-10-01 | 2026-10-05 | 2026-10-01 | 2026-10-05 | 2 bar benders
GF Beams & Slab | Superstructure | Beam Extra Bars | 7.01 | kg | 3 | 2026-10-01 | 2026-10-03 | 2026-10-01 | 2026-10-03 | 2 bar benders
GF Beams & Slab | Superstructure | Beam Stirrups | 380.22 | kg | 3 | 2026-10-01 | 2026-10-03 | 2026-10-01 | 2026-10-03 | 2 bar benders
GF Beams & Slab | Superstructure | Slab Main Bars | — |  | 1 | 2026-10-01 | 2026-10-01 | 2026-10-01 | 2026-10-01 | 3 bar benders
GF Beams & Slab | Superstructure | Slab Cross Bars | — |  | 1 | 2026-10-01 | 2026-10-01 | 2026-10-01 | 2026-10-01 | 3 bar benders
GF Beams & Slab | Superstructure | Beam Formwork | 147.22 | m² | 4 | 2026-10-06 | 2026-10-09 | 2026-10-06 | 2026-10-09 | 3 carpenters
GF Beams & Slab | Superstructure | Slab Formwork | 128.57 | m² | 4 | 2026-10-06 | 2026-10-09 | 2026-10-06 | 2026-10-09 | 3 carpenters
GF Beams & Slab | Superstructure | Beam RCC(M25) | 13.17 | m³ | 7 | 2026-10-10 | 2026-10-16 | 2026-10-10 | 2026-10-16 | 2 masons + 6 helpers
GF Beams & Slab | Superstructure | Slab RCC(M25) | — |  | 1 | 2026-10-10 | 2026-10-10 | 2026-10-10 | 2026-10-10 | 3 masons + 8 helpers
Lintel Beams | Superstructure | Beam Main Bars | 1130.18 | kg | 2 | 2026-10-17 | 2026-10-18 | 2026-10-17 | 2026-10-18 | 2 bar benders
Lintel Beams | Superstructure | Beam Stirrups | 380.22 | kg | 2 | 2026-10-17 | 2026-10-18 | 2026-10-17 | 2026-10-18 | 2 bar benders
Lintel Beams | Superstructure | Beam Formwork | 147.22 | m² | 3 | 2026-10-19 | 2026-10-21 | 2026-10-19 | 2026-10-21 | 3 carpenters
Lintel Beams | Superstructure | Beam RCC(M25) | 13.17 | m³ | 7 | 2026-10-22 | 2026-10-28 | 2026-10-22 | 2026-10-28 | 2 masons + 6 helpers
Walls | Masonry | Full Brick Wall | 42.58 | cum | 18 | 2026-10-29 | 2026-11-15 | 2026-10-29 | 2026-11-15 | 2 masons + 4 helpers
Walls | Masonry | Half Brick Wall | — | sqm | 1 | 2026-10-29 | 2026-10-29 | 2026-10-29 | 2026-10-29 | 2 masons + 3 helpers
Plumbing | Services | Plumbing Rough-in | — |  | 7 | 2026-11-16 | 2026-11-22 | 2026-11-16 | 2026-11-22 | Subcontractor
Plumbing | Services | Plumbing Testing | — |  | 3 | 2026-11-23 | 2026-11-25 | 2026-11-23 | 2026-11-25 | Subcontractor
Wiring | Services | Wiring Rough-in | — |  | 7 | 2026-11-16 | 2026-11-22 | 2026-11-16 | 2026-11-22 | Subcontractor
Wiring | Services | Wiring Testing | — |  | 3 | 2026-11-23 | 2026-11-25 | 2026-11-23 | 2026-11-25 | Subcontractor
External Plaster | Finishes | External Plaster | 129.919 | sqm | 7 | 2026-11-16 | 2026-11-22 | 2026-11-16 | 2026-11-22 | 2 masons + 2 helpers
Internal Plaster | Finishes | Internal Plaster | 269.696 | sqm | 15 | 2026-11-26 | 2026-12-10 | 2026-11-26 | 2026-12-10 | 2 masons + 2 helpers
Floor Tiles | Finishes | Floor Area | 147.642 | sqm | 13 | 2026-12-11 | 2026-12-23 | 2026-12-11 | 2026-12-23 | 2 masons + 2 helpers
Wall Tiles | Finishes | Wall Tiles | — |  | 10 | 2026-12-24 | 2027-01-02 | 2026-12-24 | 2027-01-02 | Subcontractor
Internal Painting | Finishes | Internal Painting | 269.696 | sqm | 8 | 2026-12-24 | 2026-12-31 | 2026-12-24 | 2026-12-31 | 2 painters
Internal Painting | Finishes | Wooden Door Painting | 7.414 | sqm | 1 | 2026-12-24 | 2026-12-24 | 2026-12-24 | 2026-12-24 | 2 painters
Sanitary Fittings | Fittings | Sanitary Fittings | — |  | 5 | 2027-01-03 | 2027-01-07 | 2027-01-03 | 2027-01-07 | Subcontractor
Cleaning | Handover | Cleaning & Handover | — |  | 3 | 2027-01-08 | 2027-01-10 | 2027-01-08 | 2027-01-10 | Subcontractor

## Foundation
FOUNDATION — ACTIVITY SCHEDULE
Activity | Qty | Unit | Duration | Early Start | Early Finish | Late Start | Late Finish | Total Float | Critical | Gang
Excavation | 49.91 | cum | 12 | 2026-08-06 | 2026-08-17 | 2026-08-06 | 2026-08-17 | 0 | CRITICAL | 4 helpers
PCC(1:4:8) | 2.49 | cum | 1 | 2026-08-18 | 2026-08-18 | 2026-08-18 | 2026-08-18 | 0 | CRITICAL | 1 mason + 4 helpers
Footing main bars | 180.95 | kg | 1 | 2026-08-19 | 2026-08-19 | 2026-08-19 | 2026-08-19 | 0 | CRITICAL | 2 bar benders
Footing Cross Reinforcement | 180.95 | kg | 1 | 2026-08-19 | 2026-08-19 | 2026-08-19 | 2026-08-19 | 0 | CRITICAL | 2 bar benders
Pedestal Reinforcement | 145.23 | kg | 1 | 2026-08-19 | 2026-08-19 | 2026-08-19 | 2026-08-19 | 0 | CRITICAL | 2 bar benders
Pedestal Stirrups | 75.59 | kg | 1 | 2026-08-19 | 2026-08-19 | 2026-08-19 | 2026-08-19 | 0 | CRITICAL | 2 bar benders
FDNColumn Main Bars | 182.28 | kg | 1 | 2026-08-19 | 2026-08-19 | 2026-08-19 | 2026-08-19 | 0 | CRITICAL | 2 bar benders
FDNColumn Stirrups | 31.73 | kg | 1 | 2026-08-19 | 2026-08-19 | 2026-08-19 | 2026-08-19 | 0 | CRITICAL | 2 bar benders
Footing Formwork | 18.1 | m² | 1 | 2026-08-20 | 2026-08-20 | 2026-08-20 | 2026-08-20 | 0 | CRITICAL | 2 carpenters
Pedestal Formwork | 9.87 | m² | 1 | 2026-08-20 | 2026-08-20 | 2026-08-20 | 2026-08-20 | 0 | CRITICAL | 2 carpenters
FDNColumn Formwork | 16.86 | m² | 1 | 2026-08-20 | 2026-08-20 | 2026-08-20 | 2026-08-20 | 0 | CRITICAL | 2 carpenters
FDN RCC(M25) | 10.66 | cum | 7 | 2026-08-21 | 2026-08-27 | 2026-08-21 | 2026-08-27 | 0 | CRITICAL | 2 masons + 6 helpers
Pedestal RCC(M25) | 1.169 | cum | 3 | 2026-08-21 | 2026-08-23 | 2026-08-21 | 2026-08-23 | 0 | CRITICAL | 1 mason + 4 helpers
FDNColumn RCC(M25) | 0.695 | cum | 3 | 2026-08-21 | 2026-08-23 | 2026-08-21 | 2026-08-23 | 0 | CRITICAL | 1 mason + 4 helpers
RFR (Returning and Filling) | 38.39 | m³ | 5 | 2026-08-28 | 2026-09-01 | 2026-08-28 | 2026-09-01 | 0 | CRITICAL | 4 helpers
Removal | 15.01 | m³ | 2 | 2026-08-28 | 2026-08-29 | 2026-08-28 | 2026-08-29 | 0 | CRITICAL | 4 helpers

## Plinth Beam
PLINTH BEAM — ACTIVITY SCHEDULE
Activity | Qty | Unit | Duration | Early Start | Early Finish | Late Start | Late Finish | Total Float | Critical | Gang
Beam Main Bars | 1130.18 | kg | 6 | 2026-09-02 | 2026-09-07 | 2026-09-02 | 2026-09-07 | 0 | CRITICAL | 2 bar benders
Beam Extra Bars | 7.01 | kg | 1 | 2026-09-02 | 2026-09-02 | 2026-09-02 | 2026-09-02 | 0 | CRITICAL | 2 bar benders
Beam Stirrups | 380.22 | kg | 3 | 2026-09-02 | 2026-09-04 | 2026-09-02 | 2026-09-04 | 0 | CRITICAL | 2 bar benders
Beam Formwork | 147.22 | m² | 5 | 2026-09-08 | 2026-09-12 | 2026-09-08 | 2026-09-12 | 0 | CRITICAL | 3 carpenters
Beam RCC(M25) | 13.17 | m³ | 7 | 2026-09-13 | 2026-09-19 | 2026-09-13 | 2026-09-19 | 0 | CRITICAL | 2 masons + 6 helpers

## GF Columns
GF COLUMNS — ACTIVITY SCHEDULE
Activity | Qty | Unit | Duration | Early Start | Early Finish | Late Start | Late Finish | Total Float | Critical | Gang
Column Main Bars | 363.96 | kg | 2 | 2026-09-20 | 2026-09-21 | 2026-09-20 | 2026-09-21 | 0 | CRITICAL | 2 bar benders
Column Stirrups | 101.14 | kg | 1 | 2026-09-20 | 2026-09-20 | 2026-09-20 | 2026-09-20 | 0 | CRITICAL | 2 bar benders
Column Formwork | 34.42 | m² | 2 | 2026-09-22 | 2026-09-23 | 2026-09-22 | 2026-09-23 | 0 | CRITICAL | 2 carpenters
Column RCC(M25) | 2.11 | m³ | 7 | 2026-09-24 | 2026-09-30 | 2026-09-24 | 2026-09-30 | 0 | CRITICAL | 2 masons + 4 helpers

## GF Beams & Slab
GF BEAMS & SLAB — ACTIVITY SCHEDULE
Activity | Qty | Unit | Duration | Early Start | Early Finish | Late Start | Late Finish | Total Float | Critical | Gang
Beam Main Bars | 1130.18 | kg | 5 | 2026-10-01 | 2026-10-05 | 2026-10-01 | 2026-10-05 | 0 | CRITICAL | 2 bar benders
Beam Extra Bars | 7.01 | kg | 3 | 2026-10-01 | 2026-10-03 | 2026-10-01 | 2026-10-03 | 0 | CRITICAL | 2 bar benders
Beam Stirrups | 380.22 | kg | 3 | 2026-10-01 | 2026-10-03 | 2026-10-01 | 2026-10-03 | 0 | CRITICAL | 2 bar benders
Slab Main Bars | — |  | 1 | 2026-10-01 | 2026-10-01 | 2026-10-01 | 2026-10-01 | 0 | CRITICAL | 3 bar benders
Slab Cross Bars | — |  | 1 | 2026-10-01 | 2026-10-01 | 2026-10-01 | 2026-10-01 | 0 | CRITICAL | 3 bar benders
Beam Formwork | 147.22 | m² | 4 | 2026-10-06 | 2026-10-09 | 2026-10-06 | 2026-10-09 | 0 | CRITICAL | 3 carpenters
Slab Formwork | 128.57 | m² | 4 | 2026-10-06 | 2026-10-09 | 2026-10-06 | 2026-10-09 | 0 | CRITICAL | 3 carpenters
Beam RCC(M25) | 13.17 | m³ | 7 | 2026-10-10 | 2026-10-16 | 2026-10-10 | 2026-10-16 | 0 | CRITICAL | 2 masons + 6 helpers
Slab RCC(M25) | — |  | 1 | 2026-10-10 | 2026-10-10 | 2026-10-10 | 2026-10-10 | 0 | CRITICAL | 3 masons + 8 helpers

## Staircase
STAIRCASE — ACTIVITY SCHEDULE
Activity | Qty | Unit | Duration | Early Start | Early Finish | Late Start | Late Finish | Total Float | Critical | Gang
Beam Main Bars | — |  | 1 | 2026-10-01 | 2026-10-01 | 2027-01-08 | 2027-01-08 | 99 | +99d | 2 bar benders
Beam Formwork | — |  | 1 | 2026-10-02 | 2026-10-02 | 2027-01-09 | 2027-01-09 | 99 | +99d | 3 carpenters
Beam RCC(M25) | — |  | 1 | 2026-10-03 | 2026-10-03 | 2027-01-10 | 2027-01-10 | 99 | +99d | 2 masons + 6 helpers

## Lintel Beams
LINTEL BEAMS — ACTIVITY SCHEDULE
Activity | Qty | Unit | Duration | Early Start | Early Finish | Late Start | Late Finish | Total Float | Critical | Gang
Beam Main Bars | 1130.18 | kg | 2 | 2026-10-17 | 2026-10-18 | 2026-10-17 | 2026-10-18 | 0 | CRITICAL | 2 bar benders
Beam Stirrups | 380.22 | kg | 2 | 2026-10-17 | 2026-10-18 | 2026-10-17 | 2026-10-18 | 0 | CRITICAL | 2 bar benders
Beam Formwork | 147.22 | m² | 3 | 2026-10-19 | 2026-10-21 | 2026-10-19 | 2026-10-21 | 0 | CRITICAL | 3 carpenters
Beam RCC(M25) | 13.17 | m³ | 7 | 2026-10-22 | 2026-10-28 | 2026-10-22 | 2026-10-28 | 0 | CRITICAL | 2 masons + 6 helpers

## Walls
WALLS — ACTIVITY SCHEDULE
Activity | Qty | Unit | Duration | Early Start | Early Finish | Late Start | Late Finish | Total Float | Critical | Gang
Full Brick Wall | 42.58 | cum | 18 | 2026-10-29 | 2026-11-15 | 2026-10-29 | 2026-11-15 | 0 | CRITICAL | 2 masons + 4 helpers
Half Brick Wall | — | sqm | 1 | 2026-10-29 | 2026-10-29 | 2026-10-29 | 2026-10-29 | 0 | CRITICAL | 2 masons + 3 helpers

## Subfloor
SUBFLOOR — ACTIVITY SCHEDULE
Activity | Qty | Unit | Duration | Early Start | Early Finish | Late Start | Late Finish | Total Float | Critical | Gang
Subfloor Filling | 29.528 | cum | 5 | 2026-11-16 | 2026-11-20 | 2026-11-28 | 2026-12-02 | 12 | +12d | 4 helpers
Subfloor PCC 1:3:6 | 14.764 | cum | 6 | 2026-11-21 | 2026-11-26 | 2026-12-03 | 2026-12-08 | 12 | +12d | 1 mason + 4 helpers
Subfloor PCC 1:2:4 | 11.073 | cum | 6 | 2026-11-21 | 2026-11-26 | 2026-12-03 | 2026-12-08 | 12 | +12d | 1 mason + 4 helpers
Cement Screed Bed | 2.953 | cum | 2 | 2026-11-27 | 2026-11-28 | 2026-12-09 | 2026-12-10 | 12 | +12d | 2 masons

## Plumbing
PLUMBING — ACTIVITY SCHEDULE
Activity | Qty | Unit | Duration | Early Start | Early Finish | Late Start | Late Finish | Total Float | Critical | Gang
Plumbing Rough-in | — |  | 7 | 2026-11-16 | 2026-11-22 | 2026-11-16 | 2026-11-22 | 0 | CRITICAL | Subcontractor (assumed)
Plumbing Testing | — |  | 3 | 2026-11-23 | 2026-11-25 | 2026-11-23 | 2026-11-25 | 0 | CRITICAL | Subcontractor (assumed)

## Wiring
WIRING — ACTIVITY SCHEDULE
Activity | Qty | Unit | Duration | Early Start | Early Finish | Late Start | Late Finish | Total Float | Critical | Gang
Wiring Rough-in | — |  | 7 | 2026-11-16 | 2026-11-22 | 2026-11-16 | 2026-11-22 | 0 | CRITICAL | Subcontractor (assumed)
Wiring Testing | — |  | 3 | 2026-11-23 | 2026-11-25 | 2026-11-23 | 2026-11-25 | 0 | CRITICAL | Subcontractor (assumed)

## External Plaster
EXTERNAL PLASTER — ACTIVITY SCHEDULE
Activity | Qty | Unit | Duration | Early Start | Early Finish | Late Start | Late Finish | Total Float | Critical | Gang
External Plaster | 129.919 | sqm | 7 | 2026-11-16 | 2026-11-22 | 2026-11-16 | 2026-11-22 | 0 | CRITICAL | 2 masons + 2 helpers

## Internal Plaster
INTERNAL PLASTER — ACTIVITY SCHEDULE
Activity | Qty | Unit | Duration | Early Start | Early Finish | Late Start | Late Finish | Total Float | Critical | Gang
Internal Plaster | 269.696 | sqm | 15 | 2026-11-26 | 2026-12-10 | 2026-11-26 | 2026-12-10 | 0 | CRITICAL | 2 masons + 2 helpers

## Floor Tiles
FLOOR TILES — ACTIVITY SCHEDULE
Activity | Qty | Unit | Duration | Early Start | Early Finish | Late Start | Late Finish | Total Float | Critical | Gang
Floor Area | 147.642 | sqm | 13 | 2026-12-11 | 2026-12-23 | 2026-12-11 | 2026-12-23 | 0 | CRITICAL | 2 masons + 2 helpers

## External Painting
EXTERNAL PAINTING — ACTIVITY SCHEDULE
Activity | Qty | Unit | Duration | Early Start | Early Finish | Late Start | Late Finish | Total Float | Critical | Gang
External Painting | 129.919 | sqm | 4 | 2026-11-23 | 2026-11-26 | 2027-01-07 | 2027-01-10 | 45 | +45d | 2 painters

## Wall Tiles
WALL TILES — ACTIVITY SCHEDULE
Activity | Qty | Unit | Duration | Early Start | Early Finish | Late Start | Late Finish | Total Float | Critical | Gang
Wall Tiles | — |  | 10 | 2026-12-24 | 2027-01-02 | 2026-12-24 | 2027-01-02 | 0 | CRITICAL | Subcontractor (assumed)

## Internal Painting
INTERNAL PAINTING — ACTIVITY SCHEDULE
Activity | Qty | Unit | Duration | Early Start | Early Finish | Late Start | Late Finish | Total Float | Critical | Gang
Internal Painting | 269.696 | sqm | 8 | 2026-12-24 | 2026-12-31 | 2026-12-24 | 2026-12-31 | 0 | CRITICAL | 2 painters
Wooden Door Painting | 7.414 | sqm | 1 | 2026-12-24 | 2026-12-24 | 2026-12-24 | 2026-12-24 | 0 | CRITICAL | 2 painters

## Sanitary Fittings
SANITARY FITTINGS — ACTIVITY SCHEDULE
Activity | Qty | Unit | Duration | Early Start | Early Finish | Late Start | Late Finish | Total Float | Critical | Gang
Sanitary Fittings | — |  | 5 | 2027-01-03 | 2027-01-07 | 2027-01-03 | 2027-01-07 | 0 | CRITICAL | Subcontractor (assumed)

## Light Fittings
LIGHT FITTINGS — ACTIVITY SCHEDULE
Activity | Qty | Unit | Duration | Early Start | Early Finish | Late Start | Late Finish | Total Float | Critical | Gang
Light Fittings | — |  | 5 | 2027-01-01 | 2027-01-05 | 2027-01-03 | 2027-01-07 | 2 | +2d | Subcontractor (assumed)

## Cleaning
CLEANING — ACTIVITY SCHEDULE
Activity | Qty | Unit | Duration | Early Start | Early Finish | Late Start | Late Finish | Total Float | Critical | Gang
Cleaning & Handover | — |  | 3 | 2027-01-08 | 2027-01-10 | 2027-01-08 | 2027-01-10 | 0 | CRITICAL | Subcontractor (assumed)

## Productivity Used
PRODUCTIVITY CONSTANTS (NBC/IS Standards)
Activity | Rate | Unit | Min Days (NBC) | Gang
Excavation | 4.5 | cum | 1 | 4 helpers
PCC(1:4:8) | 3 | cum | 1 | 1 mason + 4 helpers
FDN RCC(M25) | 2.5 | cum | 7 | 2 masons + 6 helpers
Pedestal RCC(M25) | 2 | cum | 3 | 1 mason + 4 helpers
FDNColumn RCC(M25) | 2 | cum | 3 | 1 mason + 4 helpers
Footing main bars | 200 | kg | 1 | 2 bar benders
Footing Cross Reinforcement | 200 | kg | 1 | 2 bar benders
Pedestal Reinforcement | 200 | kg | 1 | 2 bar benders
Pedestal Stirrups | 150 | kg | 1 | 2 bar benders
FDNColumn Main Bars | 200 | kg | 1 | 2 bar benders
FDNColumn Stirrups | 150 | kg | 1 | 2 bar benders
Footing Formwork | 25 | sqm | 1 | 2 carpenters
Pedestal Formwork | 20 | sqm | 1 | 2 carpenters
FDNColumn Formwork | 20 | sqm | 1 | 2 carpenters
RFR (Returning and Filling) | 8 | cum | 1 | 4 helpers
Removal | 10 | cum | 1 | 4 helpers
Beam RCC(M25) | 2 | cum | 7 | 2 masons + 6 helpers
Beam Formwork | 30 | sqm | 1 | 3 carpenters
Beam Main Bars | 220 | kg | 1 | 2 bar benders
Beam Extra Bars | 220 | kg | 1 | 2 bar benders
Beam Stirrups | 180 | kg | 1 | 2 bar benders
Beam Total Steel | 220 | kg | 1 | 2 bar benders
Slab RCC(M25) | 3.5 | cum | 14 | 3 masons + 8 helpers
Slab Main Bars | 250 | kg | 1 | 3 bar benders
Slab Cross Bars | 250 | kg | 1 | 3 bar benders
Slab Formwork | 40 | sqm | 1 | 3 carpenters
Slab Total Steel | 250 | kg | 1 | 3 bar benders
Column RCC(M25) | 1.5 | cum | 7 | 2 masons + 4 helpers
Column Main Bars | 200 | kg | 1 | 2 bar benders
Column Stirrups | 150 | kg | 1 | 2 bar benders
Column Formwork | 22 | sqm | 1 | 2 carpenters
Column Total Steel | 200 | kg | 1 | 2 bar benders
Full Brick Wall | 2.5 | cum | 3 | 2 masons + 4 helpers
Half Brick Wall | 3 | cum | 2 | 2 masons + 3 helpers
Subfloor Filling | 6 | cum | 1 | 4 helpers
Subfloor PCC 1:3:6 | 2.5 | cum | 1 | 1 mason + 4 helpers
Subfloor PCC 1:2:4 | 2 | cum | 1 | 1 mason + 4 helpers
Cement Screed Bed | 15 | sqm | 2 | 2 masons
Floor Area | 12 | sqm | 1 | 2 masons + 2 helpers
Wooden Door Shutter | 4 | sqm | 1 | 2 carpenters
Wooden Door Frame | 0.05 | cum | 1 | 2 carpenters
UPVC Toilet Door | 4 | sqm | 1 | 2 carpenters
UPVC Windows | 8 | sqm | 1 | 2 carpenters
UPVC Ventilators | 6 | sqm | 1 | 2 carpenters
External Plaster | 20 | sqm | 1 | 2 masons + 2 helpers
Internal Plaster | 18 | sqm | 1 | 2 masons + 2 helpers
External Painting | 40 | sqm | 1 | 2 painters
Internal Painting | 35 | sqm | 1 | 2 painters
Wooden Door Painting | 12 | sqm | 1 | 2 painters